## Slide 1: Project Management and SE Context
SE423: Software Project Management

## Slide 2: Outline
Introduction
Projects
What is Project Management?
Software Project Management
Factors in Project Success & Failure
Project Dimensions
Projects vs Programs
Suggested Skills for PM
Project Management History

## Slide 3: Introduction

## Slide 4: Learning Objectives (1 of 2)
Define the systems view of project management and how it applies to information technology (IT) projects
Summarize organizations, including the four frames, organizational structures, and organizational culture
Explain why stakeholder management and top management commitment are critical for a project’s success

## Slide 5: Learning Objectives (2 of 2)
Distinguish between project and product life cycles
Discuss the unique attributes and diverse nature of IT projects
Summarize recent trends affecting IT project management, including globalization, outsourcing, virtual teams, and agile project management

## Slide 6: A Systems View of Project Management
Projects must operate in a broad organizational environment
Project managers need to use systems thinking:
  Taking a holistic view of carrying out projects within the context of the organization

## Slide 7: What Is a Systems Approach?
A systems approach emerged in the 1950s to describe a holistic and analytical approach to management and problem solving
Three parts include:
  Systems philosophy: an overall model for thinking about things as systems
  Systems analysis: problem-solving approach
  Systems management: address business, technological, and organizational issues before making changes to systems

## Slide 8: The Three-Sphere Model for Systems Management

## Slide 9: Advice for Young Professionals
It’s difficult enough trying to understand the various technologies an organization uses. How can you begin to understand the business and organizational aspects?
  Make it a priority. Don’t just focus on the technology, no matter how exciting it seems to you. Even if you take just a few minutes each day learning about other aspects of the organization, that’s a start.
  Tell your boss or other people you work with that you want to understand how the entire organization works. Ask important questions like how the company makes money, who key customers are, what the priorities are for the year, what meetings you can attend or documents you can read to gain more knowledge, etc.
  Network, network, network! Find out which people inside or outside of your organization can help you in developing a systems approach. You might be surprised how quickly you can move up in your career once you understand the big picture.

## Slide 10: Understanding Organizations
Systems approach requires that project managers always view their projects in the context of the larger organization
Organizational issues are often the most difficult part of working on and managing projects
Important for project managers to develop a better understanding of people as well as organizations
  To improve the success rate of IT projects

## Slide 11: The Four Frames of Organizations

## Slide 12: What Went Wrong?
In a paper titled “A Study in Project Failure,” two researchers examined the success and failure of 214 IT projects over an eight-year period in several European countries
The researchers found that only one in eight (12.5 percent) were considered successful in terms of meeting scope, time, and cost goals
The authors said that the culture within many organizations is often to blame
Among other things, people often do not discuss important leadership, stakeholder, and risk management issues

## Slide 13: Organizational Structures (1 of 2)
Three basic organizational structures
  Functional: functional managers report to the CEO
  Project: program managers report to the CEO
  Matrix: middle ground between functional and project structures; personnel often report to two or more bosses; structure can be weak, balanced, or strong matrix

## Slide 14: Organizational Structures (2 of 2)

## Slide 15: Organizational Culture (1 of 2)
Organizational culture is a set of shared assumptions, values, and behaviors that characterize the functioning of an organization
Many experts believe the underlying causes of many companies’ problems are not the structure or staff, but the culture

## Slide 16: Organizational Culture (2 of 2)
Ten characteristics of organizational culture:
  Member identity*
  Group emphasis*
  People focus
  Unit integration*
  Control
  Risk tolerance*
  Reward criteria*
  Conflict tolerance*
  Means-ends orientation
  Open-systems focus*
*Project work is most successful in an organizational culture where these items are strong/high and other items are balanced.

## Slide 17: Focusing on Stakeholder Needs
Project managers must take time to identify, understand, and manage relationships with all project stakeholders
Using the four frames of organizations can help meet stakeholder needs and expectations
Senior executives/top management are very important stakeholders
See Chapter 13, Project Stakeholder Management, for more information

## Slide 18: The Importance of Top Management Commitment
People in top management positions are key stakeholders in projects
A very important factor in helping project managers successfully lead projects is the level of commitment and support they receive from top management
Without top management commitment, many projects will fail.
Some projects have a senior manager called a champion who acts as a key proponent for a project.

## Slide 19: The Importance of Top Management Commitment
How top management can help project managers
  Providing adequate resources
  Approving unique project needs in a timely manner
  Getting cooperation from other parts of the organization
  Mentoring and coaching on leadership issues

## Slide 20: Best Practice
IT governance addresses the authority and control for key IT activities in organizations, including IT infrastructure, IT use, and project management
A lack of IT governance can be dangerous, as evidenced by three well-publicized IT project failures in Australia
  Sydney Water’s customer relationship management system
  The Royal Melbourne Institute of Technology’s academic management system
  One.Tel’s billing system

## Slide 21: The Need for Organizational Commitment to Information Technology
If the organization has a negative attitude toward IT, it will be difficult for an IT project to succeed
Having a Chief Information Officer (CIO) at a high level in the organization helps IT projects
Assigning non-IT people to IT projects also encourage more commitment

## Slide 22: The Need for Organizational Standards
Standards and guidelines help project managers be more effective
Senior management can encourage
  the use of standard forms and software for project management
  the development and use of guidelines for writing project plans or providing status information
  the creation of a project management office or center of excellence

## Slide 23: Project and Product Life Cycles
It is good practice to divide projects into several phases
  Because projects operate as part of a system and involve uncertainty
The same can be said for developing products

## Slide 24: Project Life Cycle (1 of 2)
A project life cycle is a collection of project phases that defines
  what work will be performed in each phase
  what deliverables will be produced and when
  who is involved in each phase, and
  how management will control and approve work produced in each phase
A deliverable is a product or service produced or provided as part of a project

## Slide 25: Project Life Cycle (2 of 2)
In early phases of a project life cycle
  resource needs are usually lowest
  the level of uncertainty (risk) is highest
  project stakeholders have the greatest opportunity to influence the project
In middle phases of a project life cycle
  the certainty of completing a project improves
  more resources are needed
The final phase of a project life cycle focuses on
  ensuring that project requirements were met
  the sponsor approves completion of the project

## Slide 26: Product Life Cycles (1 of 3)
Products also have life cycles
The Systems Development Life Cycle (SDLC) is a framework for describing the phases of developing information systems
Systems development projects can follow
  Predictive life cycle
  Iterative life cycle
  Incremental life cycle
  Adaptive life cycle
  Hybrid life cycle

## Slide 27: Product Life Cycles (2 of 3)
Predictive Life Cycle Models
  Waterfall model: has well-defined, linear stages of systems development and support
  Spiral model: shows that software is developed using an iterative or spiral approach rather than a linear approach
  Prototyping model: used for developing prototypes to clarify user requirements
  Rapid Application Development (RAD) model: used to produce systems quickly without sacrificing quality

## Slide 28: Product Life Cycles (3 of 3)

## Slide 29: The Importance of Project Phases and Management Reviews
A project should successfully pass through each of the project phases in order to continue on to the next
Management reviews, also called phase exits, phase gate reviews, or kill points, should occur after each phase to evaluate the project’s progress, likely success, and continued compatibility with organizational goals
It is unwise to wait until the end of project or product phases to have management inputs
  Many projects are reviewed by management on a regular basis

## Slide 30: What Went Right?
"The real improvement that I saw was in our ability toin the words of Thomas Edisonknow when to stop beating a dead horse.…Edison's key to success was that he failed fairly often; but as he said, he could recognize a dead horse before it started to smell...In information technology we ride dead horsesfailing projectsa long time before we give up. But what we are seeing now is that we are able to get off them; able to reduce cost overrun and time overrun. That's where the major impact came on the success rate.”*
Many organizations, like Huntington Bancshares, Inc., use an executive steering committee to help keep projects on track.
Some projects still go on a long time before being killed, like Blizzard’s Titan game project.
*Cabanis, Jeannette, "'A Major Impact': The Standish Group's Jim Johnson On Project Management and IT Project Success," PM Network, PMI, Sep.1998, p. 7

## Slide 31: The Context of Information Technology Projects
Project context
  Has a critical impact on which product development life cycle will be most effective for a particular software development project
Several issues unique to the IT industry have a critical impact on managing IT projects

## Slide 32: The Nature of IT Projects
IT projects can be very diverse in terms of size, complexity, products produced, application area, and resource requirements
The nature of software development projects is even more diverse than hardware-oriented projects
IT projects also support every possible industry and business function

## Slide 33: Characteristics of IT Project Team Members
IT project team members often have diverse backgrounds and skill sets
Many companies purposely hire graduates with degrees in other fields such as business, mathematics, or the liberal arts to provide different perspectives on IT projects
Some IT projects require the skills of people in just a few job functions
  But some require inputs from many or all of them

## Slide 34: Diverse Technologies
IT projects use diverse technologies that change rapidly
Differences in technical knowledge can make communication between professionals challenging
New technologies have also shortened the time frame many businesses have to develop, produce, and distribute new products and services

## Slide 35: Recent Trends Affecting Information Technology Project Management
Globalization
Outsourcing: Outsourcing is when an organization acquires goods and/or sources from an outside source. Offshoring is sometimes used to describe outsourcing from another country
Virtual teams: A virtual team is a group of individuals who work across time and space using communication technologies
Agile project management

## Slide 36: Globalization
Issues
  Communications
  Trust
  Common work practices
  Tools
Suggestions
  Employ greater project discipline
  Think globally but act locally
  Consider collaboration over standardization
  Keep project momentum going
  Use newer tools and technology

## Slide 37: Outsourcing
Organizations remain competitive by using outsourcing to their advantage, such as finding ways to reduce costs
Practice can be unpopular on some countries
Project managers should become more familiar with many global and procurement issues

## Slide 38: Virtual Teams (1 of 2)
Advantages
  Lowering costs because many virtual workers do not require office space or support beyond their home offices
  Providing more expertise and flexibility or increasing competitiveness and responsiveness by having team members from across the globe working any time of day or night
  Improving the work/life balance for team members by eliminating fixed office hours and the need to travel to work

## Slide 39: Virtual Teams (2 of 2)
Disadvantages
  Isolating team members
  Increasing the potential for communications problems
  Reducing the ability for team members to network and transfer information informally
  Increasing the dependence on technology to accomplish work
See text for a list of factors that help virtual teams succeed, including team processes, trust/relationships, leadership style, and team member selection

## Slide 40: Agile (1 of 2)
Agile means being able to move quickly and easily, but some people feel that project management, as they have seen it used, does not allow people to work quickly or easily
Early software development projects often used a waterfall approach
  As technology and businesses became more complex, the approach was often difficult to use because requirements were unknown or continuously changing
Agile today means using an approach where requirements and solutions evolve through collaboration

## Slide 41: Agile (2 of 2)
Manifesto for Agile Software Development
  In February 2001, a group of 17 people that called itself the Agile Alliance developed and agreed on the Manifesto for Agile Software Development, as follows:
  “We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
    Individuals and interactions over processes and tools
    Working software over comprehensive documentation
    Customer collaboration over contract negotiation
    Responding to change over following a plan”*
*Agile Manifesto.

## Slide 42: Scrum (1 of 4)
According to the Scrum Alliance, Scrum is the leading agile development method for completing projects with a complex, innovative scope of work.
The term was coined in 1986 in a Harvard Business Review study that compared high-performing, cross-functional teams to the scrum formation used by rugby teams.

## Slide 43: Scrum (2 of 4)

## Slide 44: Scrum (3 of 4)
Kanban
  Technique that can be used in conjunction with Scrum
  Developed in Japan by Toyota Motor Corporation
  Uses visual cues to guide workflow
  Kanban cards show new work, work in progress, and work completed

## Slide 45: Scrum (4 of 4)
The PMBOK® Guide describes best practices for what should be done to manage projects.
Agile is a methodology that describes how to manage projects.
The Project Management Institute (PMI) recognized the increased interest in Agile, and introduced a new certification in 2011 called Agile Certified Practitioner (ACP).
Seasoned project managers understand that they have always had the option of customizing how they run projects, but that project management is not easy, even when using Agile.

## Slide 46: Chapter Summary
Project managers need to take a systems approach when working on projects
Organizations have four different frames: structural, human resources, political, and symbolic
The structure and culture of an organization have strong implications for project managers
Projects should successfully pass through each phase of the project life cycle
Project managers need to consider several factors due to the unique context of information technology projects
Recent trends affecting IT project management include globalization, outsourcing, virtual teams, and agile project management

## Slide 48: Four Pillars

## Slide 49: The Use of Process

## Slide 50: The Use of Process

## Slide 51: Cone of Uncertainty

## Slide 54: Project Managers
Growing demand for software project managers
  Organizations have become customer-driven.
  Organizations have evolved from function to process structures.
  Organizations are using task forces more frequently.
  Organizations have become more project-oriented.
From the organization perspective, project managers are needed to:
  Gain market share
  Be first to market
  Stay profitable
  Maintain Quality

## Slide 55: Project Managers
Project Managers are mainly responsible for all issues related to the software project; issues may vary depending on the project scale, some of the common issues are:
  Schedule
  Budget
  Quality
  Delivery of products
  Locking in resources
Bottom line, as a project manager you will notice that most of your time is consumed chasing and collecting the status of project tasks.

## Slide 56: The Field
Jobs: where are they?
Professional Organizations
  Project Management Institute (PMI) (pmi.org)
    The Project Management Institute (PMI) is an international professional society for project managers founded in 1969
  Software Engineering Institute (SEI)
  IEEE Software Engineering Group
Tools
  MS Project
Notes: monster.com search “project management”
See everything from this class
Bridge Technical and non-technical
Other Certs don’t matter
Hundreds of PM programs like MS-Project
Project: the illusion of control

## Slide 57: PMI & the PMP certification
The Project Management Institute (PMI: http://www.pmi.org/) is the leading organization in advancing the project management profession
Certifications
  PMI PMP
The “PMBOK” – PMI Body of Knowledge
PMI has more than 450,000 (as of 2013) members in 185 countries
Provides support in:
  Education and training—seminars, program certification
  Professional development and networking—Global Congresses
  Professional standards and certification—standards for project-related activities (the PMBOK, scheduling, portfolios)
The Project Management Professional (PMP) certification is amongst the most valuable certifications in the IT field

## Slide 58: The Field Part 2
Average Entry Level PM salary $69,000
In San Jose, an Entry Level Project Manager can make $88,568, which is 20.9% higher than the national median.
The median annual Program Manager salary is $120,195, as of March 24, 2016, with a range usually between $103,414-$138,009.
Contract rates for PM's can match techies
PMI certification adds avg. 14% to salary
PMI certificates, 1993: 1,000; 2002: 40,000; 2017: 450,000

## Slide 59: The Project Manager
The Role of the Project Manager
Job descriptions vary, but most include responsibilities like planning, scheduling, coordinating, and working with people to achieve project goals
Remember that 97% of successful projects were led by experienced project managers, who can often help influence success factors
Skills for Project Managers
Project managers need a wide variety of skills
They should:
  Be comfortable with change
  Understand the organizations they work in and with
  Be able to lead teams to accomplish project goals

## Slide 60: Competencies for Project Managers
People skills
Leadership
Listening
Integrity, ethical behavior, consistent
Strong at building trust
Verbal communication
Strong at building teams
Conflict resolution, conflict management
Critical thinking, problem solving
Understands, balances priorities
Negotiating
Influencing the Organization
Mentoring
Process and technical expertise

## Slide 61: Software Project Management
Fundamentals

## Slide 62: Formal Project Management
Advantages of Using Formal Project Management
Better control of financial, physical, and human resources
Improved customer relations
Shorter development times
Lower costs
Higher quality and increased reliability
Higher profit margins
Improved productivity
Better internal coordination
Higher worker morale (less stress)
  Less “death marches”
  Less overworked personnel

## Slide 63: Conventional Software Management Performance
Barry Boehm's “Industrial Software Metrics Top 10 List”:
Finding and fixing a software problem after delivery costs 100 times more than finding and fixing the problem in early design phases
You can compress software development schedules 25%, but no more
For every $1 you spend on development, you will spend $2 on maintenance
Software development and maintenance costs are primarily a function of source lines of code.
Variations among people account for the biggest difference in software productivity; hire good people to succeed.

## Slide 64: Conventional Software Management Performance
Barry Boehm's “Industrial Software Metrics Top 10 List”:
The overall ratio of software to hardware costs is still growing.
Only about 15% of software development effort is devoted to programming
Software systems and products typically cost 3 times as much per SLOC as individual software programs. Software system products (system of systems) costs 9 times as much
Walkthroughs catch 60% of the errors
80% of the contributions comes from 20% of the contributors.

## Slide 65: First Principles
One size does not fit all
Spectrums
  Project types
  Sizes
  Formality and rigor
Notes: Like families, each dysfunctional in it's own “special way”
Classic Mistakes later == Anti
Different sizes need different choices from the PM

## Slide 66: Strategy
Hope is not a strategy.
So what is our strategy?
Classic Mistake Avoidance
Development Fundamentals
Risk Management
Schedule-Oriented Practices

## Slide 67: PMI's 9 Knowledge Areas
Project integration management
Scope
Time
Cost
Quality
Human resource
Communications
Risk
Procurement
Notes: If you study for the PMI certification you’ll need to know these

## Slide 68: Project Management Framework

## Slide 69: What is a project life cycle?
The project life cycle is a collection of sequential or overlapping project phases
  The phases divide the project into logical blocks of related activities
  This division into phases simplifies management, planning, and control
Phases within the project are defined by technical information transfer or technical component hand-off
  Example: Inception and elaboration phases in the Unified Process
  Example: Releases in Agile life cycles

## Slide 70: Phases
The completion and approval of one or more deliverables (deﬁned as measurable, veriﬁable work products) deﬁnes the endpoint of a project phase
Different phases can have different relationships among themselves, even within the same project
  Sequential relationship. A phase starts only when the previous phase is complete
  Overlapping relationship. A new phase can be planned and started before the previous phase is complete
This class focuses on sequential phases with iterative and incremental or adaptive sub-phases

## Slide 71: PMBOK project life cycles
In a predictive life cycle:
  Product and deliverables are deﬁned at the beginning of the project
  Changes to scope are carefully–and restrictively–managed
In an iterative and incremental life cycle:
  Project phases repeat one or more project activities, taking advantage of increased understanding of the product
  Each phase (and each iteration within a phase) successively adds to the functionality of the product
  Scope is usually well-deﬁned early in the project life cycle, but can be changed with relatively low overhead as project proceeds
In an adaptive life cycle [Agile]:
  Product is developed over multiple phases, each with several iterations
  Detailed scope is deﬁned for each phase only as the phase begins

## Slide 72: IT project life cycles
IT projects have two concurrent life cycles:
  Project life cycle (PLC) encompasses all activities of project, including the System/Software Development Life Cycle (SDLC)
  PLC is directed toward achieving project requirements
  SDLC is directed toward achieving product requirements
Both life cycle models are needed to manage an IT project
  PLC alone will not adequately address system development concerns
  SDLC alone will not adequately address business and product integration concerns
  Effective integration of the two life cycle models is essential to improving the likelihood of project success
In effect, the PLC and the SDLC should be so closely interwoven that they need not be distinguished from each other

## Slide 73: What is a project life cycle?
Consists of a number of generally sequential phases
Phases are defined by technical information transfer or technical component hand-off
Cost and staffing levels vary as a function of time according to the following qualitative schematic diagram:

## Slide 74: What is a project life cycle?
Risk of failure is greatest at start of project when the level of uncertainty is highest
Stakeholder influence over project product decreases as project continues
Project life cycles define:
  Technical work to be done in each phase
  When deliverables are to be generated in each phase
  How each deliverable is reviewed, verified, and validated
  Who is involved in each phase
  How to control each phase
  How to approve each phase

## Slide 75: Phases in project life cycle
The completion and approval of one or more deliverables (measurable, verifiable work product) defines a project phase
In iterative systems development, new phase can be started without closing the previous phase
A phase can be closed without initiating subsequent phase

## Slide 76: Project & product life cycles

## Slide 77: The systems development lifecycle
“The systems development life cycle (SDLC) is the process of understanding how an information system (IS) can support business needs by designing a system, building it, and delivering it to users”*
A methodology is a formalized approach to implementing the SDLC
What differentiates one methodology from another:
  The specific activities that must be performed
  When, how, and how often the activities are performed
  Who performs the activities
  The amount of emphasis placed on an activity at a specific point in time
* Dennis, Alan (2012-05-01). Systems Analysis and Design with UML, 4th Edition (Page 2). Wiley. Kindle Edition.

## Slide 78: Software Development Process
Ad hoc
  Code and Fix
  Rapid Prototyping
Prescriptive
  Linear/sequential (Classic and Waterfall)
  Evolutionary (Iterative/incremental or spiral)
  Unified Process
Adaptive
  Lean and agile methods
Notes: SE 425
April 3, 2008
Lecture 1
78/85
SE 425
April 3, 2008
Lecture 1
78/108
Lecture 1
January 8, 2008
SE 425
78/108

## Slide 79: Sequential (‘waterfall’) methodology
The term waterfall was coined by Winston Royce in a 1970 paper titled Managing the Development of Large Software Systems, in the Proceedings of IEEE WESCON
The paper used the sequential waterfall approach as an example of an ill-conceived, risk-prone practice for developing large systems
Royce advocated a series of iterative feedback loops among the development stages, incrementally gaining learning value from working software
Instead of adopting the approach Royce advocated, managers and practitioners adopted its anti-form, without feedback loops

## Slide 80: Waterfall SDLC
Each phase is marked by completion of Deliverables
The primary software project phases:
  Requirements
  Analysis
  Design
  Construction
  Quality Assurance (aka Testing)
  Deployment

## Slide 81: Waterfall SDLC

## Slide 82: Project Phases A.K.A.

## Slide 83: Waterfall system development model
Highly-sequential process
Failure symptoms:
  Protracted integration and late design breakage
  Late risk resolution
  Requirements-driven functional decomposition
  Adversarial stakeholder relationships
  Focus on documents and review meetings
Still followed (in name or practice) by many organizations, usually a modified version

## Slide 84: Waterfall system development model
Sequential: suitable projects and management approaches
A sequential SDLC is suitable for projects with:
  Clear, unambiguous, and stable user requirements
  Familiar, proven technology
  Low complexity
  Adequate time
  Stable schedule
A project meeting most of these criteria can use conventional project management practices, such a big, up-front planning and conventional risk assessment

## Slide 85: Evolutionary methodologies
An evolutionary methodology follows an iterative and incremental approach that allows the start of development with incomplete, imperfect knowledge
An iterative and incremental process is like solving a jigsaw puzzle: neither top-down nor bottom-up but accretionary and convergent
An iterative and incremental process offers these advantages:
  Logical progress toward evolving a robust architecture
  Effective management of changing requirements
  Effective means to address changes in planning
  Ability to perform continuous integration
  Early understanding of the system (the ‘Hello world!’ effect)
  Ongoing risk assessment
Evolutionary methodologies are incremental at both the macro (project- scale) and micro (working team) process levels

## Slide 86: Iterative system development model
Non-linear approach to system development
Incorporates top five principles of modern development processes:
  Architecture first. Provides the central design element
  Iterative life-cycle process. Provides the essential risk management element
  Component-based development. Provides the technology element
  Change management environment. Provides the control element
  Round-trip engineering. Provides the automation element

## Slide 87: 5,000 foot view of Iterative SDLC
Iterative SD model defines four life-cycle phases:
  Inception
  Elaboration
  Construction
  Transition
We iterate through each phase, and repeat as needed.
Now, for a quick survey of the phases…

## Slide 88: Inception phase
Essential activities
  Formulate product scope. Capture requirements and operational concept
  Perform feasibility analysis. Determine whether the organization has the resources and technical capabilities to meet customer's needs
  Synthesize the system architecture. Evaluate essential system design constraints and trade-offs, as well as available solutions
  Plan and prepare business case. Address risk management, staffing, iteration plans, cost, and infrastructure

## Slide 89: Elaboration phase
Most critical phase of the four
Essential activities
  Elaborate the vision. Detail elements of the vision that drive architectural or planning decisions
  Elaborate the process and infrastructure. The construction process and environment are established here
  Elaborate the architecture and select reusable (internal or COTS) components. Baseline the architecture as quickly as possible and demonstrate that the architecture will support the vision at reasonable cost in reasonable time

## Slide 90: Construction phase
Essential activities
  Achieve useful versions (intermediate, alpha, beta, and other test releases)
  Perform resource management, control, and process optimization
  Complete component development and test
  Assess product releases against acceptance criteria

## Slide 91: Transition phase
Essential activities
  Perform deployment-specific engineering tasks. Commercial packaging and production, sales kit development, field personnel training
  Assess deployment baselines against complete vision and acceptance criteria. Examine and compare what is being delivered to what was envisioned and delineated by acceptance criteria
  Plan for next iteration

## Slide 92: Comparative expenditure profiles
Waterfall |  | Iterative | 
Activity | Cost | Cost | Activity
Management | 5% | 10% | Management
Requirements | 5% | 10% | Requirements
Design | 10% | 15% | Design
Code & Unit Testing | 30% | 25% | Implementation
Integration & Test | 40% | 25% | Assessment
Deployment | 5% | 5% | Deployment
Environment | 5% | 10% | Environment
Total | 100% | 100% | Total
Based on and adapted from Tables 1-1 and 10-1 in
Software Project Management: A Unified Approach by Walker Royce

## Slide 93: Suitable Projects And Management Approaches
An evolutionary SDLC is suitable for projects with:
  Reasonably–but not perfectly–clear user requirements
  Unfamiliar or unproven technology
  High complexity
  Short time schedule
  Schedule variability
Such a project would use rolling wave planning rather than big, up-front planning and use a continuous, adaptive approach to risk assessment and management

## Slide 94: Agile Project Management

## Slide 95: Agile Projects
Lean methodology. Only as much process as necessary.
'Agile' is an umbrella term used for identifying various models used for agile development, such as Scrum.
Since agile development model is different from conventional models, agile project management is a specialized area in project management.

## Slide 96: Agile Projects
Agile project management is an iterative approach to planning and guiding project processes.
An agile project is completed in small sections called iterations, or, in scrum, sprints.
Each iteration is reviewed and critiqued by the project team, which may include representatives of the client business as well as employees.
Insights gained from the critique of an iteration are used to determine what the next step should be in the project.
Each project iteration is typically scheduled to be completed within two weeks.
Notes: http://searchcio.techtarget.com/definition/Agile-project-management

## Slide 97: Agile Project Steps
The product owner identifies the product vision.
The product owner creates a product roadmap.
The product owner creates a release plan.
The product owner, the (scrum) master, and the development team plan sprints, also called iterations, and start creating the product within those sprints
During each sprint, the development team has daily meetings [called scrums].
The team holds a sprint review.
The team holds a sprint retrospective.
Notes: http://www.dummies.com/how-to/content/agile-project-management-for-dummies-cheat-sheet.navId-410850.html

## Slide 98: Agile Project Artifacts
Product vision statement: An elevator pitch, or a quick summary, to communicate how your product supports the company's or organization's strategies. The vision statement must articulate the goals for the product. Revisit once a year.
Product roadmap: The product roadmap is a high-level view of the product requirements, with a loose time frame for when you will develop those requirements. Revisit twice a year.
Release plan: A high-level timetable for the release of working software.
Product backlog: The full list of what is in the scope for your project, ordered by priority. Once you have your first requirement, you have a product backlog.
Sprint backlog: The goal, user stories, and tasks associated with the current sprint.
Increment: The working product functionality at the end of each sprint.
Notes: http://www.dummies.com/how-to/content/agile-project-management-for-dummies-cheat-sheet.navId-410850.html

## Slide 99: Agile Project Roles
Development team: The group of people who do the work of creating a product. Programmers, testers, designers, writers, and anyone else who has a hands-on role in product development is a member of the development team.
Product owner: The person responsible for bridging the gap between the customer, business stakeholders, and the development team. The product owner is sometimes called a customer representative.
Scrum master: The person responsible for supporting the development team, clearing organizational roadblocks, and keeping the agile process consistent. A scrum master is sometimes called a project facilitator.
Stakeholders: Anyone with an interest in the project.
Agile mentor: Someone who has experience implementing agile projects and can share that experience with a project team. The agile mentor can provide valuable feedback and advice to new project teams and to project teams that want to perform at a higher level.
Notes: http://www.dummies.com/how-to/content/agile-project-management-for-dummies-cheat-sheet.navId-410850.html

## Slide 100: Agile Project Events
Project planning: The initial planning for your project.
  includes creating a product vision statement and a product roadmap,
  can take place in as little time as one day.
Release planning: Planning the next set of product features to release
Sprint: A short cycle of development, in which the team creates potentially shippable product functionality.
Sprint planning: A meeting at the beginning of each sprint where the scrum team commits to a sprint goal.
Daily scrum: A 15-minute meeting held each day in a sprint, where development team members state what they completed the day before, what they will complete on the current day, and whether they have any roadblocks.
Notes: http://www.dummies.com/how-to/content/agile-project-management-for-dummies-cheat-sheet.navId-410850.html

## Slide 101: Agile Project Events
Sprint review: A meeting at the end of each sprint, where the development team demonstrates the working product functionality it completed during the sprint.
Sprint retrospective: A meeting at the end of each sprint where the scrum team discusses what went well, what could change, and how to make any changes.
Notes: http://www.dummies.com/how-to/content/agile-project-management-for-dummies-cheat-sheet.navId-410850.html

## Slide 102: Selection considerations: guiding questions
Organizational characteristics
  What are the characteristics of the organizational culture? What are the management comfort levels with the various methodologies?
  How open is management and the organization to change?
  Is the organization risk-tolerant or risk-adverse?
  What is the organization's tolerance for real risk vs. perceived risk?
Project characteristics
  How large is the project?
  What is the project's estimated duration?
  Are teams co-located or distributed?
  Is regulatory compliance a signiﬁcant factor?
  How ﬂexible are documentation requirements?

## Slide 103: Selection considerations: guiding questions
People and management characteristics
  What are the experience levels of team members?
  Are team members self-motivated or command-driven?
  What sort of management style is employed? Laissez-faire, micromanagement, or somewhere in-between?
  What sort of social dynamics govern project efforts within the organization? Cooperative and problem-solving, adversarial, or blaming?

## Slide 104: Methodology characteristics compared

## Slide 105: Examples: Applying the table
Short time schedule + shifting user requirements
  Agile
Complex + short time schedule
  Iterative
Clear user requirements + long time schedule + command-driven team
  Water-fall
Reliable + complex + schedule variability
  Agile
Unfamiliar technology + short time schedule + schedule variability
  Either Agile or Iterative

## Slide 106: Software Project Management
Project organization
  Putting a process in place
  Software process
  Phases for software project management

## Slide 107: Process
A process encapsulates an organization's experience in form of successful recipes.
Process descriptions, generally, contain the sequence of steps to be executed, who executes them, the entry/exit criteria for major steps, etc.
Guidelines, checklists, and templates provide support to use the processes.
Processes
Checklists
Guidelines
Activity
Templates
Review

## Slide 108: Putting a Process in Place
Choosing a Process.
  All projects have a process, unfortunately some don’t specify and implement their process.
  Projects with no specified process end up thrashing.
  Thrashing, unproductive work, can quickly cripple a project.
Generally, there are two choices for choosing a process:
  Tailor the organizational process to your project.
    Used when most of the people are from the same group as before
    Used when the last project was successful.
  Specify a process for your project.
    Good when people are from different organizations using different processes

## Slide 109: Tailoring a Process
Steps to Tailoring an Organizational Process:
  Determine how your project differs from the typical organizational project.
  Form two lists: activities your project needs from the organizational process and tasks your project doesn’t need from the process
  Propose changes to the organizational process
  Circulate the tailored process within the team and other key personnel for review and input.
  Integrate the changes and move quickly for closure.

## Slide 110: Assessing the Process
Assessing should be an ongoing process through out the project.
Both the project and the process should lend themselves to assessment and improvement.
Make gathering measurements part of concurrent documentation.
Gather data to answer the following:
  Were the tasks and supporting activities effective?
  How much effort did each task and activity require?
  What tasks and activities were performed but weren’t in the process specification?
  How did the products change over time?
  When did tasks and activities start and stop?
  How did tasks and activities integrate?
  When in the project did we spend effort doing what?
Repeat this during project close out.

## Slide 111: The Project Manager: Responsibilities
Project planning
Managing the project
Lead project team
Building client partnerships
Targeting to the business

## Slide 112: Few Rules Before We Embark
And finally, communicate, communicate, and communicate!
Richness of communication channel
Communication Effectiveness
people in a
conference room with whiteboard
phone
email
Videotape
Paper
people
on Video
Conferencing

## Slide 113: Recap
Definition of a Project
A project is a sequence of unique, complex, and connected activities having one goal or purpose and that must be completed by a specific time, within budget, and according to specification.
What is a Program?
A program is a collection of projects.
The projects must be completed in a specific order for the program to be considered complete. Because they compromise multiple projects, they are larger in scope than a single project.

## Slide 114: Project Parameters
Five constraints operate on every project:
  Scope
  Quality
  Cost
    Time
    Resources
A change in one of these constraints can cause a change in another constraint to restore the equilibrium of the project
Let's discuss each one of these in detail …

## Slide 115: Scope

## Slide 116: Project Parameters
Scope
Scope is a statement that defines the boundaries of the project. It tells not only what will be done but also what will not be done.
In the information systems industry, scope is often referred to as a functional specification.
In the engineering profession, it is generally called a statement of work.
Quality
Two types of quality are part of every project:
  The first is product quality. This refers to the quality of the deliverable form of the project.
  The second type of quality is process quality, which is the quality of the project management itself. The focus is on how well the project management process works and how can it be improved. Continuous quality improvement and process quality management are the tools used to measure process quality.

## Slide 117: Project Parameters
Cost – The X-amount of dollars that it will cost to do the project is another variable that defines the project; the budget that has been established for the project.
  This is an important factor for projects that create deliverables that are sold to external customers
Time – The customer specifies a timeframe within which the project must be completed.
  Cost and time are inversely related to one another. The time a project takes to be completed can be reduced, but cost increases as a result.
Resources – Resources are assets, such as people, equipment, physical facilities, or inventory, that have limited availabilities, can be scheduled, or can leased from an outside party. Some are fixed, others are variable only in the long term. In any case, they are central to the scheduling of project activities and the orderly completion of the project.

## Slide 118: 5,000 foot view of PM processes
PMBOK Guide collects the forty-four defined PM processes into five Project Management Process Groups
  Initiating
  Planning
  Executing
  Monitoring & Controlling
  Closing
Now, we’ll take a quick survey of the processes in each group …

## Slide 119: Phases of the Project Management
There are five phases of the project management life cycle:
  Scope/Define/Initiate – Scope the project
  Plan – Develop the project plan
  Execute – Launch the plan
  Monitor – Monitor/control project progress
  Close – Close out the project
Note: these can be repeated for each phase
Each process/phase/activity is described by:
  Inputs
  Tools & Techniques
  Outputs
Notes: projects are composed of processes

## Slide 120: Initiating Process
Develop project charter
  State the problem/opportunity.
  Concerned with authorizing a project
  May be used for a whole project
  May be used for a single project phase in a large, multiphase project
Develop preliminary project scope statement
  Concerned with producing a preliminary, high-level definition of project
  Broadly defines what is and what is not part of the project
Establish the project plan.
  Define the project objectives.
  Identify the success criteria.
  List assumptions, risks, obstacles

## Slide 121: Initiating Process
Inputs
  Product Description
  Strategic plan
  Project Selection Criteria
  Historical Information
Outputs
  Project Charter
  Project Manager assigned
  Constraints
  Assumptions

## Slide 122: Planning Process
Scope Planning
Scope Definition
Activity Definition
Activity Sequencing
Activity Duration Estimating
Resource Planning
Cost Estimating
Cost Budgeting
Schedule Development
Quality Planning
Communications Planning
Organization Planning
Staff Acquisition
Risk Planning
Procurement Planning
Project Plan Development
Devising and maintaining a workable scheme to accomplish the business need that the project was undertaken to address

## Slide 123: Develop the project plan
Develop project management plan
  Concerned with creating and integrating all sub-plans into a single source of information
  Identify the project activities.
Scope planning
  Concerned with how the project scope statement will be created
Create WBS
Scope definition
  Concerned with actual creation of project scope statement
Activity definition
  Activity sequencing
  Activity duration estimating
  Activity resource estimating
Determine resource requirements.

## Slide 124: Planning processes
Schedule development
  Concerned with analyzing activity outputs (definition, etc.) to create project schedule
Construct/analyze the project network.
Cost estimating **
Cost budgeting
  Concerned with aggregating costs of individual activities to establish cost baseline
Quality planning *
  Concerned with quality standards and how to achieve them
Human resource planning *
Communications planning *
* indicates minimal or no coverage
** indicates optional coverage

## Slide 125: Planning processes
Risk management planning
  Concerned with how to carry out risk management activities
  Risk identification
  Qualitative risk analysis
    Concerned with prioritizing risks based on probability of occurrence and impact
  Quantitative risk analysis *
  Risk response planning
    Concerned with mitigating risks to project objectives
Plan purchases and acquisitions *
  Concerned with what, when, and how of purchases and acquisitions
Plan contracting *
Prepare the project proposal.

## Slide 126: Executing Process
Project Plan Execution
Scope Verification
Quality Assurance
Acquire project team
  Identify and organize the project team.
  Establish team operating rules.
  Team Development
Solicitation
  Information Distribution
  Source Selection
  Contract Administration
Level project resources.
Schedule work packages.
Document work packages.
Coordinating people and other resources to carry out the plan
Notes: Direct and manage project execution
  Concerned with directing technical and organizational entities to execute work defined in PM plan
Perform quality assurance
  Concerned with applying planned quality activities
Acquire project team
Develop project team
  Concerned with improving competencies and interaction of project members
Information distribution *
Request seller responses *
Select sellers *

## Slide 127: Monitoring & Controlling Process
Monitor and control project work
  Ensuring that project objectives are met by monitoring and measuring progress and taking corrective measures when necessary
  Concerned with acquiring and assessing performance information to effect process improvements
Integrated change control
  Overall Change Control
  Scope Change Control
  Schedule Control
Scope control – Concerned with changes to project scope
Scope verification – Concerned with acceptance of project deliverables
Schedule control – Concerned with changes to project schedule

## Slide 128: Monitoring & Controlling Process
Cost control * – Concerned with changes to the project budget
Quality Control – Concerned with monitoring quality compliance of project results and correcting unsatisfactory results
Manage project team – Concerned with tracking performance, providing feedback, and coordinating changes
  Define problem-escalation process.
  Monitor project progress versus plan.
  Establish progress reporting systems.
  Performance reporting * – Concerned with status, progress, and forecasting
Install change control tools/process.
Risk monitoring and control
Manage stakeholders
Contract administration *
Revise project plans.

## Slide 129: Close out the project
Formalizing acceptance of the project or phase and bringing it to an orderly end
Administrative Closure
  Concerned with finalizing all activities across all Process Groups
  Complete project documentation.
  Complete post-implementation audit.
    Lessons learned
  Issues final project report.
Contract Close-out
  Concerned with completing and settling all contracts
  Obtain client acceptance.
  Install project deliverables.

## Slide 130: Phases of the Project Management
Level of Activity and Overlap of Process Groups Over Time

## Slide 131: Project Processes & Their Integration
Project Management Processes (Principles of Project Management)
  Initiating processes (Defining)
  Planning processes
  Executing processes
  Monitoring & controlling processes
  Closing processes
System Development Processes (Iterative/evolutionary)
  Inception phase
  Elaboration phase
  Construction phase
  Transition phase
Integrating IT Project Processes
  PM/IT project integration tactics

## Slide 132: PM/IT process integration tactics
Wherever possible, establish common policies, processes, and procedures between IT and PM groups
Identify an integration manager to link IT and PM groups
Use a common, integrated, consistent vocabulary that is continuously updated to facilitate inter- (as well as intra-) group communications
Ensure that project manager possesses suitable process integration skills and is familiar with IT risks
Involve IT analysts in development of business requirements
Identify an ombudsman to quickly resolve issues that arise between PM and IT groups

## Slide 133: Project & SDLC integration waterfall development model
Initiating
Closing
Planning
Executing
Monitoring & Controlling
PM Process Groups
Concept
Requirements
Design
Code & Unit Testing
Integration & Test
Deployment
Waterfall SDLC Phases

## Slide 134: Phases in iterative* system life cycle
Engineering Stage
Production Stage
Inception
Elaboration
Construction
Transition
Idea
Architecture
Intermediate
Releases
Product
Establish that the
system is viable
Establish the
ability to
build the system
within
constraints
Build the
intermediate
internal releases
of the
system
Roll out a fully-
functional
system to the
customer
Phases
* I often interchange iterative & evolutionary
The stages below are repeated (iterative) – see notes
Notes: In an iterative development the four phases (Inception, Elaboration, Construction and Transition) are repeated iteratively. Each time they add features to the product. There is also a phase where there is more planning.

## Slide 135: Project & SDLC integration iterative/incremental development model
Product
Release
Milestone
Engineering Stage
Production Stage
Inception
Elaboration
Construction
Transition
Idea
Architecture
Intermediate
Releases
Product
Establish that the
system is viable
Establish the
ability to
build the system
within
constraints
Build the
intermediate
internal releases
of the
system
Roll out a fully-
functional
system to the
customer
Objectives
Milestone
Architecture
Milestone
Initial Operational
Capability Milestone
Initiating
Closing
Planning
Executing
Monitoring & Controlling
PM Process Groups
Notes: In an iterative development the four phases (Inception, Elaboration, Construction and Transition) are repeated iteratively. Each time they add features to the product. There is also a phase where there is more planning.
In each iteration we plan for the next iteration.

## Slide 136: Project & SDLC integration iterative development model
Planning in the iterative development model
  Needs to take into consideration the iterations
  See PMBOK-SWE Ch. 2.4.2.3
  See also: Kruchten, P (2002, Oct 15) Planning an Iterative Project: http://www.ibm.com/developerworks/rational/library/2831.html

## Slide 137: Project Management Tools

## Slide 138: Project Management Tools
There are many tools available
MS-Project is an example of these tools
Basic requirements
  Develop a Work Breakdown Structure
  Build network diagram (aka PERT chart)
  Build Gantt chart
  Assign resources
  Calculate critical path and critical chain
What is the difference between critical path and critical chain?
  Critical chain also manages buffer activity durations and resources

## Slide 139: PM Tools: Software
Low-end
  Basic features, tasks management, charting
  MS Excel, Milestones Simplicity
Mid-market
  Handle larger projects, multiple projects, analysis tools
  MS Project (approx. 50% of market)
High-end
  Very large projects, specialized needs, enterprise
  AMS Realtime
  Primavera Project Manager

## Slide 140
Breaks project into a hierarchy.
Creates a clear project structure.
Avoids risk of missing project elements.
Enables clarity of high level planning.
Work Breakdown Structure

## Slide 141: Tools: Gantt Chart

## Slide 142: Tools: Network Diagram