## Slide 1: Project Management Process Groups
SE423: Software Project Management

## Slide 2: Outline
Introduction
Initiating processes
Planning processes
Execution processes
Controlling and Monitoring processes
Closing processes
Agile and Scrum

## Slide 3: Introduction

## Slide 4: Learning Objectives
Describe the five project management process groups, the typical level of activity for each, and the interactions among them
Relate the project management process groups to the project management knowledge areas
Discuss how organizations develop information technology (IT) project management methodologies to meet their needs
Review a case study of an organization applying the project management process groups to manage an IT project, describe outputs of each process group, and understand the contribution that effective initiating, planning, executing, monitoring and controlling, and closing make to project success

## Slide 5: Learning Objectives
Review a case study of the same project managed with an agile focus and compare the key differences between an agile approach and a predictive approach
Describe several templates for creating documents for each process group

## Slide 6: Introduction
Project management consists of 10 knowledge areas
  Integration, scope, schedule, cost, quality, resource, communications, risk, procurement, and stakeholder management
Projects involve five project management process groups
  Initiating, planning, executing, monitoring and controlling, and closing
    Tailoring these process groups to meet individual project needs increases the chance of success in managing projects

## Slide 7: Project Management Process Groups
A process is a series of actions directed toward a particular result
  Project management can be viewed as a number of related processes
Project management process groups
  Initiating processes
  Planning processes
  Executing processes
  Monitoring and controlling processes
  Closing processes

## Slide 8: Mapping the Process Groups to the Knowledge Areas
You can map the main activities of each PM process group into the ten knowledge areas
  Note that there are activities from each knowledge area under the planning process groups

## Slide 9: Developing an IT Project Management Methodology
Many organizations develop their own internal IT project management methodologies
  A methodology describes how things should be done
  A standard describes what should be done
Different project management methodologies
  PRojects IN Controlled Environments (PRINCE2)
  Agile
  Rational Unified Process (RUP)
  Six Sigma
  DevOps

## Slide 10: Global Issues
PMI published (Pulse of the Profession®2021) for Middle East & North Africa (MENA)

## Slide 11: Global Issues
PMI published (Pulse of the Profession®2021) for Middle East & North Africa (MENA)

## Slide 12: What Went Right?
Organizations that excel in project management complete 89 percent of their projects successfully compared to only 36 percent of organizations that do not have good project management processes
PMI estimates that poor project performance costs over $109 million for every $1 billion invested in projects and programs

## Slide 13: Case Study: JWD Consulting’s Project Management Intranet Site (Predictive Approach)
This case study provides an example of what’s involved in initiating, planning, executing, controlling, and closing an IT project
  You can download templates for creating your own project management documents from the companion website for this text or the author’s site
Note: this case study provides a big picture view of managing a project
  Later chapters provide detailed information on each knowledge area

## Slide 14: Initiating processes

## Slide 15: Project Pre-Initiation and Initiation
Initiating includes recognizing and starting a new project
  Right kinds of projects for the right reasons
Strategic planning should serve as the foundation for deciding which projects to pursue
  Expresses the vision, mission, goals, objectives, and strategies of the organization
  Provides the basis for IT project planning

## Slide 16: Pre-initiation Tasks
It is good practice to lay the groundwork for a project before it officially starts
Senior managers often perform several pre-initiation tasks
  Determine the scope, time, and cost constraints for the project
  Identify the project sponsor
  Select the project manager
  Develop a business case for a project
  Meet with the project manager to review the process and expectations for managing the project
  Determine if the project should be divided into two or more smaller projects

## Slide 17: Initiating (1 of 5)
Knowledge Area | Initiating Process | Initiating Process
Project Integration Management | Develop project charter | Project charter Assumption log
Project Stakeholder Management | Identify stakeholders | Stakeholder register Change requests Project management plan updates Project documents updates
Project initiation knowledge areas, processes, and outputs

## Slide 18: Initiating (2 of 5)
Name | Position | Internal/External | Project Role | Contact Information
Joe Fleming | CEO | Internal | Sponsor | joe_fleming@jwdconsulting.com
Erica Bell | PMO Director | Internal | Project Manager | erica_bell@jwdconsulting.com
Michael Chen | Senior Consultant | Internal | Team Member | michael_chen@jwdconsulting.com
Kim Phuong | Business Analyst | External | Advisor | kim_phuong@client1.com
Louise Mills | PR Director | Internal | Advisor | louise_mills@jwdconsulting.com
Stakeholder Register

## Slide 19: Initiating (3 of 5)
Name | Level of Interest | Level of Influence | Potential Management Strategies
Joe Fleming | High | High | Joe likes to stay on top of key projects and make money. Have a lot of short, face-to-face meetings and focus on achieving the financial benefits of the project.
Louise Mills | Low | High | Louise has a lot of things on her plate, and she does not seem excited about this project. She may be looking at other job opportunities. Show her how this project will help the company and her resume.
Stakeholder Management Strategy

## Slide 20: Initiating (4 of 5)
Drafting the project charter
  See Table 3-6 for an example
Holding a project kick-off meeting
  It’s good practice to hold a kick-off meeting at the beginning of a project so that stakeholders can meet each other, review the goals of the project, and discuss future plans

## Slide 21: Initiating (5 of 5)

## Slide 22: Planning processes

## Slide 23: Project Planning
The main purpose of project planning is to guide execution
  Every knowledge area includes planning information (see Table 3-7)
Key outputs included in the JWD project
  Team contract
  Project scope statement
  Work breakdown structure (WBS)
  Project schedule, in the form of a Gantt chart with all dependencies and resources entered
  List of prioritized risks (part of a risk register)
See sample documents

## Slide 24: Project Planning

## Slide 25: Project Planning
Ranking | Potential Risk
1 | Lack of inputs from internal consultants
2 | Lack of inputs from client representatives
3 | Security of new system
4 | Outsourcing/purchasing for the article retrieval and Ask the Expert features
5 | Outsourcing/purchasing for processing online payment transactions
6 | Organizing the templates and examples in a useful fashion
7 | Providing an efficient search feature
8 | Getting good feedback from Michael Chen and other senior consultants
9 | Effectively promoting the new system
10 | Realizing the benefits of the new system within one year
List of Prioritized Risks

## Slide 26: Execution processes

## Slide 27: Project Execution
Usually takes the most resources to perform
  Project managers must use their leadership skills to handle the many challenges that occur during project execution
Listing the knowledge areas, executing processes, and outputs of project execution
  Many project sponsors and customers focus on deliverables related to providing the products, services, or results desired from the project
  It is equally important to document change requests and update planning documents
A milestone report can help focus on completing major milestones

## Slide 28: Project Execution
The actions performed during this process include:
  Performing the activities needed to meet the project objectives
  Obtaining and manage quotations, bids and proposals as needed
  Managing the project team and manage other resources
  Collecting and analyze performance data
  Generating project data for status reports and forecasts
  Managing risks
  Conducting change control and implementing approved changes
  Establishing and managing project communication channels
  Collecting and documenting lessons learned

## Slide 29: Project Execution
The Execution Phase will broadly involve several actions.
The priority or sequence is entirely dependent on the nature of the project and organizational practices and preferences.
But nevertheless, they are performed to enable successful project execution.

## Slide 30: Project Execution Actions
Acquire Develop & Manage the Team who will work on the project.
Execute Project Scope.
Recommend changes, bug fixes, preventive and corrective actions.
Timely Communication with all stakeholders.
Implemented approved changes to the processes, documentation and plans.
Team Building exercises.
Give recognition and rewards to team members and keep them motivated.
Hold Status Review meetings to ensure project is on track and any deviations are attended to at the earliest.
Use Work Authorization systems to allocate work.
Request Seller responses to your tender and outsourcing needs.
Select Seller for your procurement needs.

## Slide 31: Project Execution
Project execution involves:
  Establishing and managing the project team.
  Coordinating people and resources.
  Monitoring team performance.
  Contracting procurements.
  Directing and managing project execution.
  Distributing information.
  Performing quality assurance activities.

## Slide 32: Project Execution
The items produced by project execution are:
  The risk and issue management responses plus corrective actions.
  The deliverables themselves plus work performance information.
  Change requests.
  Negotiation and influence to ensure appropriate staff are assigned.
  Motivation building and mentoring to ensure the team performance.
  Conflict resolution and problem solving.
  Procurements and contracts are negotiated and put in place.
  Organizational process assets are updated as a result of executing the project plan.

## Slide 33: Project Execution

## Slide 34: Best Practice
One way to learn about best practices in project management is by studying recipients of PMI’s Project of the Year award
  The Quartier international de Montreal (QIM), Montreal’s international district, was a 66-acre urban revitalization project in the heart of downtown Montreal
  This $90 million, five-year project turned a once unpopular area into a thriving section of the city with a booming real estate market and has generated $770 million in related construction

## Slide 35: Monitoring and Controlling processes

## Slide 36: Project Monitoring and Controlling
Project monitoring and control helps you measure project performance.
Use the process to look at the project plan, review project status, identify potential problems, and implement changes when necessary.
This phase coincides with the execution phase of the project lifecycle.
You can use this phase to keep a project on schedule and within budget while also managing risk and avoiding scope creep.
At the end of the monitoring and control phase, the customer accepts the completed project deliverables.

## Slide 37: Project Monitoring and Controlling
Involves measuring progress toward project objectives, monitoring deviation from the plan, and taking correction actions
  Affects all other process groups and occurs during all phases of the project life cycle
Outputs include performance reports, change requests, and updates to various plans

## Slide 38: Project Monitoring and Controlling
The primary purpose of monitoring and control in project management is to identify problems before they occur and make adjustments.
These changes may require reevaluating and updating the project plan.

## Slide 39: Project Monitoring and Controlling
Involves tracking, reviewing, and regulating project progress
Includes status reporting, progress measurement, and forecasting
Reports on scope, schedule, cost, resources, quality, and risks
Controls project and project document changes
Includes control of scope, schedule, costs, and risks
Formalizes acceptance of deliverables
Records quality control results
Implements risk treatment plans and actions
Administers suppliers

## Slide 40: Project Monitoring and Control Process
The process helps project teams discover problems before they occur.
  Monitor Key Performance Indicators (KPIs)
  Monitor Change Requests
  Monitor Project Scope
  Identify Risks
  Communicate with Team Members, Stakeholders, and Clients

## Slide 41: Project Monitoring and Controlling
The key outputs are:
  Progress and status reports
  Plan updates
  Risks registers
  Change requests
  Work products/deliverables

## Slide 42: Project Monitoring and Controlling
Reporting mechanisms are time-sensitive.
Slow reporting mechanisms hinders controlling the project.
The control framework will vary from project to project, reflecting the size and complexity of the project and the extent to which the different levels of management are involved in it.

## Slide 43: Closing processes

## Slide 44: Project Closing
Involves gaining stakeholder and customer acceptance of the final products and services
  Even if projects are not completed, they should be closed out to learn from the past
Outputs may include project files and lessons-learned reports
  Also may include a final report and presentation

## Slide 45: Project Closing
When it comes to project management, closing out a project isn’t just a matter of executing deliverables.
Though the process may seem tedious or overly administrative, a formal closure phase ensures all loose ends are tied up, documentation is signed and approved, contractors are paid, and everyone is on the same page.
The closing phase also gives you the opportunity to review and evaluate the project’s success (or failure), which is crucial for planning and executing successful projects in the future.

## Slide 46: What is project closure?
The closing phase of project management is the stage where all deliverables are finalized and formally transferred, and all documentation is signed off, approved, and archived.
The project closure process ensures that:
  All work has been completed according to the project plan and scope.
  All project management processes have been executed.
  You have received final sign-off and approval from all parties.
  The project management closure process also gives the team the opportunity to review and evaluate the project’s performance to ensure future projects’ success.

## Slide 47: Importance of closing a project
Project closure helps avoid:
  Repeating mistakes on future projects and objectives
  Having final products or deliverables without dedicated support and resources
  Failing to identify the team or individuals who will own and maintain the solution following final delivery
  Creating liability issues resulting from incomplete payments, contracts, or deliverables

## Slide 48: 7 steps to closing a project
The closing phase of project management involves several steps.
Work through the following checklist to ensure your project is successfully completed.
Formally transfer all deliverables
  Finalize and transfer the project deliverables to the client.
  Go through your project plan to identify all deliverables and make sure they have been fully completed and handed off.
Confirm project completion
  It’s not enough to declare a project done yourself.
  Each person involved needs to agree on the project’s completion before you can formally close it out and move on.
  To confirm the project’s completion, obtain approvals for the project deliverables (i.e., all stakeholders must agree that you delivered on all parts of the project plan) with official sign-offs from the project stakeholders.

## Slide 49: 7 steps to closing a project
Review all contracts and documentation
  Review all the project documentation to ensure all parties have been paid for the work and there are no outstanding invoices.
Release resources
  Formally release resources from the project, including suppliers, contractors, team members, and any other partners.
Conduct a post-mortem
  A post-mortem is one of the most valuable steps of the project closure process.
  This is a time to review the successes, failures, and challenges of the project and identify opportunities for improvement going forward.

## Slide 50: 7 steps to closing a project
Archive documentation
  Finalize all documentation (contracts, project plans, scope outline, costs, schedule, etc.) and index them in the company archives for later reference.
Celebrate
  Finally, don’t forget to celebrate!
  The end of a project is a big accomplishment and represents the culmination of many hours of hard work and dedication from a team of contributors.

## Slide 51: Case Study 2: JWD Consulting’s Project Management Intranet Site (Agile Approach)
An agile project team typically uses several iterations or deliveries of software instead of waiting until the end of the project to provide one product
  Teams do not normally make a snap decision about whether to manage a project using an agile approach or not

## Slide 52: Agile and Scrum

## Slide 53: Scrum Roles, Artifacts, and Ceremonies (1 of 5)
Product owner: person responsible for the business value of the project and for deciding what work to do and in what order, as documented in the product backlog
ScrumMaster: person who ensures that the team is productive, facilitates the daily Scrum, enables close cooperation across all roles and functions, and removes barriers that prevent the team from being effective
Scrum team or development team: cross-functional team of five to nine people who organize themselves and the work to produce the desired results for each sprint, which normally lasts two to four weeks

## Slide 54: Scrum Roles, Artifacts, and Ceremonies (2 of 5)
An artifact is a useful object created by people
Scrum artifacts
  Product backlog: list of features prioritized by business value
  Sprint backlog: highest-priority items from the product backlog to be completed within a sprint
  Burndown chart: shows the cumulative work remaining in a sprint on a day-by-day basis

## Slide 55: Scrum Roles, Artifacts, and Ceremonies (3 of 5)
Scrum ceremonies
  Sprint planning session: meeting with the team to select a set of work from the product backlog to deliver during a sprint
  Daily Scrum: short meeting for the development team to share progress and challenges and plan work for the day
  Sprint reviews: meeting in which the team demonstrates to the product owner what it has completed during the sprint
  Sprint retrospectives: meeting in which the team looks for ways to improve the product and the process based on a review of the actual performance of the development team

## Slide 56: Scrum Roles, Artifacts, and Ceremonies (4 of 5)

## Slide 57: Scrum Roles, Artifacts, and Ceremonies (5 of 5)
Process Group | Scrum Activity
Initiating | 
 | Determine roles
 | Decide how many sprints will compose each release and the scope of software to deliver
Planning | 
 | Create product backlog
 | Create sprint backlog
 | Create release backlog
 | Plan work each day in the daily Scrum
 | Document stumbling blocks in a list
Executing | 
 | Complete tasks each day during sprints
 | Produce a shippable product at the end of each sprint
Unique Scrum activities by process group

## Slide 58: Project Pre-Initiation and Initiation
Main differences between pre-initiation in this case and the first case
  Determining roles and deciding what functionality would be delivered as part of each release
  How many sprints will be required to complete a release
  How many releases of software to deliver

## Slide 59: Planning (1 of 3)
Because Scrum implies that team members work as a self-directed group, coached by the ScrumMaster, a team charter should not be necessary
Descriptions of work are identified in the product and sprint backlogs
More detailed work is documented in technical stories
Team must estimate a velocity or capacity for each sprint

## Slide 60: Planning (2 of 3)

## Slide 61: Planning (3 of 3)
Product Backlog | Sprint Backlog
1. User story templates, samples, and point person | 1. User story templates, samples, and point person
2. WBS templates, samples, and point person | 2. WBS templates, samples, and point person
3. Project schedule templates, samples, and point person | 3. Project schedule templates, samples, and point person
4. Ability to charge customers for some intranet products and services | 4. Ability to charge customers for some intranet products and services
5. Ability to collect user suggestions | 5. Ability to collect user suggestions
6. Business case templates, samples, and point person | 
7. Ask the Expert feature | 
8. Stakeholder management strategy templates, samples, and point person | 
9. Risk register templates, samples, and point person | 
10. Etc. | 
Product and Sprint Backlogs

## Slide 62: Executing
The most time and money should be spent on executing
  Plans are implemented to create the desired product
Agile approach: team produces several iterations of a potentially shippable product
  Users can access and make suggestions
Communications are different
  Project team meets every morning, physically or virtually

## Slide 63: Monitoring and Controlling (1 of 2)
The two main tools for monitoring and controlling in the Scrum framework
  Daily Scrum: held each morning to plan and communicate work for the day and discuss any risks, issues, or blockers
  Sprint review: work progress within a sprint can be represented on a sprint board maintained by the ScrumMaster
    Burndown chart: an important artifact used to graphically display progress on each sprint

## Slide 64: Monitoring and Controlling (2 of 2)

## Slide 65: Closing
After the sprint review, the ScrumMaster leads a sprint retrospective
  Team reflects on what happened during the sprint
Sprint retrospective is intended to answer two fundamental questions
  What went well during the last sprint that we should continue doing?
  What could we do differently to improve the product or process?

## Slide 66: Templates by Process Group
Table 3-20 lists several templates used to prepare the documents shown in this chapter and later chapters
  Download these and additional templates in one compressed file from the Companion website for this text or from the author’s website.

## Slide 67: Advice for Young Professionals
Most organizations have templates for many different kinds of documents
  Ask your boss, co-workers, and other colleagues for templates
  If you don’t like the templates you find, look at other sources
  If you can improve them, share your work with others
Templates are great, but completed templates with good information are even more useful

## Slide 68: Chapter Summary
The five project management process groups are initiating, planning, executing, monitoring and controlling, and closing
You can map the main activities of each process group to the ten knowledge areas
Some organizations develop their own information technology project management methodologies
The JWD Consulting case study provides an example of using the process groups and shows several important project documents
The second version of the same case study illustrates how to use Scrum, the leading agile method, to manage the project

## Slide 71: Initiating the Project

## Slide 72: Initiating processes overview
Initiating processes deﬁne a new project or new phase of an existing project
Initial project scope, project stakeholders, and project manager are identiﬁed
Key purposes are to:
  Align the stakeholders' expectations with project purpose
  Give stakeholders visibility into project scope and objectives
  Demonstrate that stakeholder participation helps ensure project success
All of these set the vision of the project: what needs to be accomplished

## Slide 73: Initiating Processes
Develop Project Charter
  This process falls under the Project Integration Management knowledge area
  Justiﬁes and formally authorizes a project or a project phase
  Documents the stakeholders’ initial requirements and expectations
  Forms the basis for the partnership between the requesting (customer) and performing (supplier) organizations
Identify Stakeholders
  This process falls under the Project Communications Management knowledge area
  Identiﬁes all people or organizations impacted by the project
  Documents their interests and involvement with the project, as well as their potential impact on project success
  Forms the basis for developing a strategy to approach and involve each stakeholder to maximize positive inﬂuences and minimize negative inﬂuences

## Slide 74: Concept Exploration
The “Why” phase
Not a “mandatory formal” phase
  Sometimes called the “pre-project” phase
Collecting project ideas
  Then the “funneling” process
Project Justification
  ROI – Return on Investment
  Cost-benefit analysis
  Competitive analysis (if appropriate)
Initial planning and estimates

## Slide 75: Concept Exploration
Possibly includes Procurement Management:
  RFP Process
  Vendor selection
  Contract management
Gathering the initial team
  Including PM if not already on-board
Identify the project sponsor
  Primary contact for approval and decision making
Potential Phase Outputs:
  Concept Document, Product Description, Proposal, SOW, Project Charter

## Slide 76: Concept Exploration
Characteristics & Issues
Lack of full commitment and leadership
Some frustrations:
  Management only getting rough estimates from development
  Development not getting enough specifics from customer
  Finding a balanced team
Budget sign-off may be your 1st major task
Achieved via:
  Good concept document or equivalent
  Demonstration of clear need (justification)
  Initial estimates

## Slide 77: Inputs, tools & techniques, and outputs
Inputs
  Project statement of work
  Business case
  Agreements
  Enterprise environmental factors
  Organizational process assets
Tools & Techniques
  Expert judgement
  Facilitation techniques
Outputs
  Project charter

## Slide 78: Define the Project
There is a need for clear understanding of exactly what is to be done. Project definition starts with the Conditions of Satisfaction document based on conversation with the customer.
Project Overview Statement aka Charter or Vision is generated from the Conditions of Satisfaction document.
  The Project Overview Statement clearly states what is to be done.
  Once the Project Overview Statement is approved, the scoping phase is complete.
In most cases the Project Overview Statement, the Statement of Work, and Project Charter are the same. Even scope will fit here. We will use them interchangeably.

## Slide 79: Project Charter
Activities
  Define scope
  Document Project Risks, Assumptions, and Constraints
  Identify and Perform Stakeholder Analysis
  Develop Project Charter
  Obtain Project Charter Approval
Deliverables
  Project charter
  Statement of work (SOW) (aka Scope)
Notes: PMP Chapter 2

## Slide 80: Preliminary Scope
Project objectives
Product description
Deliverables
Constraints
Assumptions
Project acceptance criteria

## Slide 81: Project Charter
The Conditions of Satisfaction statement provides the input we need to generate the Charter.
The Charter is a short document that concisely states what is to be done in the project, why it is to be done, and what business value it will provide to the organization when completed.
The main purpose of the Charter is to secure senior management approval and the resources needed to develop a detailed project plan.
It will be reviewed by the managers who are responsible for setting priorities and deciding what projects to support. It is also a general statement, it is not detailed technical statement.
A high-level project description:
  Business need, product, assumptions
Often precedes SOW
Often 2-4 pages (can be longer)

## Slide 82: Project Charter
Typical outline
  Overview
    Business need
      Problem/opportunity
    Objectives
      Project goal
    Method or approach
  General scope of work
    Success criteria
  Rough schedule & budget
  Roles & responsibilities
  Assumptions, risks, obstacles

## Slide 83: Project charter content
Project purpose or justiﬁcation
  Deﬁne the reason why the project is being done, by referring to any of the Initiating process inputs [See the “vision statement”]
Measurable project objectives and related success criteria
  Scope. Scope needed to achieve project goals and measurable criteria for scope success
  Time. Goals for timely completion and speciﬁc dates for success
  Cost. Goals for project expenditures and range of costs for success
  Quality. Quality criteria and speciﬁc measures for criteria for success
  Other. Any other objectives along with measurable criteria of success

## Slide 84: Project charter content
High-level requirements
  Describe the high-level product capabilities that satisfy stakeholder needs and expectations. Do not include detailed requirements
    Example: As a retail customer, I want to shop by either brand or by product category
    Example: As the site owner, I want a retail customer to ﬁnd a stocked product on the site within three (3) mouse clicks
    Anti-example: As the site owner, I want the products to be displayed in a 4- across grid against a light grey background

## Slide 85: Project charter content
Assumptions and constraints
  An assumption is “a thing that is accepted as true or as certain to happen, without proof”
    Example: The site will allow all site visitors to access all public features of the site
  A constraint is a limitation or restriction
    Example: The site must use a hosting service for the new site

## Slide 86: Project charter content
High-level project description and boundaries [scope]
  Provide an executive-summary-level description of the project, identify what will and will not be included in the project
    Example: The site is a one-stop source for health and wellness information … It will not provide direct access to the HR site.
High-level risks
  Risks represent any major areas of uncertainty for the project
  Risks may be internal or external
    Example: Existing customers may have difﬁculty transitioning to new site
    Example: The company does not have sufﬁcient in-house Web design expertise to match the goals for the new site

## Slide 87: Project charter content
Summary milestone schedule
  Identify any signiﬁcant points or events in the project, such as key deliverables, beginning or ending of phases, or product acceptance
  Include estimated completion dates for the milestones
    Examples: Requirements document complete: 1/31/2017; Web site on-line with training: 6/30/2017
Summary budget
  Provide a rough order of magnitude (ROM) estimate of expenditures schedule for project
    ROM estimates may be as broad as ±100% but usually range ±35%
  Budget should break down total expenditures by major categories (software, hardware, human resources, etc.)

## Slide 88: Project charter content
Stakeholder list
  A stakeholder is “a[n] individual, group, or organization who may affect, be affected by, or perceive itself to be affected by a decision, activity, or outcome of a project”*
  Identify a preliminary list of the most critical project stakeholders–this list will be reﬁned later
Project approval requirements
  Identify any criteria that must be met in order for the project to be accepted by the project customer
  Example: The project must implement the set of ‘must-have’ user stories agreed upon at project initiation
Notes: *PMBOK Guide, 5th Edition

## Slide 89: Project charter content
Project manager, responsibility, and authority levels
  Stafﬁng. Speciﬁc authority project manager is granted to hire/ﬁre, discipline, or accept/reject project staff
  Budget management and variance. Speciﬁc authority project manager is granted to commit, manage, and control project funds; also, what variance requires higher approval
  Technical decisions. Speciﬁc authority project manager is granted regarding deliverable technical decisions or project approach
  Conﬂict resolution. Speciﬁc authority the project manager is granted to resolve team and organizational conﬂict, as well as conﬂict with external stakeholders
  Escalation path for authority limitations. Deﬁne the path for escalation of issues exceeding the project manager’s authority
Name and authority of the sponsor or other person(s) authorizing the project charter
Notes: *PMBOK Guide, 5th Edition

## Slide 90: Develop Project Charter: Data Flow Diagram

## Slide 91: Statement of Work (SOW)
A description of the work required for the project; normally this is used when the project is being contracted out, but most of this is part of the Project Overview or Charter
Sets the “boundary conditions”
SOW vs. CSOW (Contract SOW)
  Latter: uses legal language as part of a competitive bidding scenario
Can be used in the final contract – be careful, be specific, be clear
Typically done after approval (after “Go”)
Can be multiple versions
  List of deliverables for an RFP
  More detailed within final RFP
  Binding version from contract

## Slide 92: SOW Template

## Slide 93: S.M.A.R.T. characteristics for Goal
Doran’s S.M.A.R.T. characteristics provide the criteria for a goal statement:
  Specific: Be specific in targeting and objective.
  Measurable: Establish measurable indicator(s) of progress.
  Assignable: Make the object assignable to one person for completion.
  Realistic: State what can realistically be done with available resources.
  Time-related: State when the objective can be achieved; that is, duration

## Slide 94: The Project Definition Statement : PDS
Just as the customer and the project manager benefit from the Charter, the project manager and project team can benefit from a closely related document, which we call the Project Definition Statement (PDS).
The PDS uses the same form as the Charter but incorporates considerably more detail. The detailed information provided in the PDS is for the use of the project manager and the project team.

## Slide 95: Charter
Tips on writing the charter
Distribution of project by type
  In-house, contract/for-hire, startup
Distribution of project by technology
  Web, Windows/Mac OS/Linux, Mobile, No platform
Distribution by industry
  Financial Services, Law, Retail
A reminder why no two projects are same
Most important elements
  Why, who, what, what not
  A little bit of when
Make sure it's clear
Some more re-purposed than others
  Occasionally read more like business plans

## Slide 96: Charter
Make the stakeholder relationships clear
  You, sponsor, user, etc.
If “for real” you’d want additional assumptions and scope constraint
The justification or cost-benefit analysis “materializes” in some of the Charters
Don’t shortchange downstream activities
  Integration, testing, rollout, etc.
Risks
  Business risks vs. Project risks
    Ex: “lack of market adoption” vs. “inexperienced team”
Functionality
  “Forgotten” items: user registration, help, security
Good out of scope items
  Internationalization
  Search system

## Slide 97: Charter
Formalities
  Spell check.
  Proof read
  Make sure your name is on first page and also header and/or footer on each page.

## Slide 98: To Get to the Essence of a Project
Why is the system being developed?
What will be done?
When will it be accomplished?
Who is responsible?
Where are they organizationally located?
How will the job be done technically and managerially?
How much of each resource (e.g., people, software, tools, database) will be needed?
Barry Boehm

## Slide 99: The project charter & agile
The project charter sets out the earliest deﬁnition for the project
  Note: PMI has eliminated an earlier (v. 3) Deﬁne Preliminary Scope Statement from among the PMBOK processes, which further deﬁned and constrained the project
The agile product overview document provides a high-level view of the most essential project elements that parallels the charter
  The product overview is less detailed and more flexible

## Slide 100: Product overview document content
Product Name
Product Vision Statement. Include both product problem statement and product position statement
Dedicated Team. List names of team members
Project Manager
Customer/Product Owner. Customer or customer representative
Architecture. Specify if constrained; else, to be determined by team
Features Backlog. High-level list of major features
Product Roadmap. Releases with themes and corresponding features
Risks/Opportunities. Consider market, project, and product aspects
Success Criteria. What the customer considers most critical criteria
Flexibility Matrix. Trade-off matrix of time, resources, and objectives

## Slide 101: Agile initiating process
Obtain input and feedback from customer and team on project objectives and justiﬁcations as part of vision meeting
If needed, prepare ‘barely sufﬁcient’ business case and associated documentation required by the company and/or project approval board in order to obtain project approval
Use an agile software development methodology and prepare accordingly

## Slide 102: Stakeholders

## Slide 103: Project stakeholders
Project stakeholders are individuals or organizations who have inﬂuence over, or are inﬂuenced by project execution or completion
Different stakeholders have varying amounts of inﬂuence, responsibility, or authority over a project
Stakeholders can have a positive, neutral, or negative inﬂuence on a project
Identifying all stakeholders associated with a project may be difﬁcult
  Stakeholders that are overlooked almost inevitably have a negative impact on project

## Slide 104: Interactions / Stakeholders
External people
  Project sponsor
  Executives
  Customers
  Contractors
  Functional managers
  Users
Team
  Architects
  System Engineers
  Designers
  Developers
  Testers
  Documenters
As a PM, who do you interact with? Project Stakeholders
Notes: Project stakeholders are individuals or organizations who have influence over, or are influenced by project execution or completion
Have varying amounts of influence, responsibility, or authority over project
May be difficult to identify all stakeholders
Stakeholders that are overlooked almost inevitably have a negative impact on project
Stakeholders can have a positive, neutral, or negative influence on project
managing all stakeholder expectations is challenging – conflict

## Slide 105: Key project stakeholder roles
Customer. Person or organization that acquires product
User. Person or organization that uses product
Performing organization. Organization performing work of project
Project manager. Responsible for managing project
Project management team. Individuals directly involved in project management activities
Project team members. Individuals performing work of project
Sponsor. Entity providing financial resources for project
Influencers. Entities indirectly affecting project
PMO. Project management office. Responsible for centralized and coordinated management of all projects under its supervision

## Slide 106: Signiﬁcant project stakeholders
Functional managers. Manage within functional or administrative areas of the business, such as human resources, accounting, or procurement. Do not deal directly with products or services
Operations management. Manage within core business areas, such as research and development, design, manufacturing, testing, or maintenance. Deal directly with producing and maintaining products
Sellers. External companies or individuals that enter into contractual agreements to provide components or services necessary for project. Also known as vendors, suppliers, or contractors
Business partners. External companies or individuals that have a closer relationship with enterprise, providing expertise or ﬁlling speciﬁc roles such as installation, training, or support

## Slide 107: Stakeholders
Senior managers who define the business issues that often have significant influence on the project.
Project (technical) managers who must plan, motivate, organize, and control the practitioners who do software work.
Practitioners who deliver the technical skills that are necessary to engineer a product or application.
Customers who specify the requirements for the software to be engineered and other stakeholders who have a peripheral interest in the outcome.
End-users who interact with the software once it is released for production use.

## Slide 108: Software System Stakeholders
Each stakeholder has different concerns:
Components
Connectors
Class/Pattern
Data flow
Reuse
Flexibility
Extensibility
Developer
Maintainability
Portability
Feasibility
Reusability
Extensibility
Flexibility
The ilities
Architect
Requirements
Cost
Schedule
Performance
Reliability
Security
Customer
Cost
Schedule
Requirements
Process
Resources
Manager
Functionality
Requirements
Regression
Tools
Simulators
Tester

## Slide 109: Stakeholder Triad
Function Representative
  The ‘business person’, Business Analyst (BA)
  Or SME: Subject Matter Expert
Executive Sponsor
  Project's visionary & champion
  Also the ‘General’, ‘Fall Guy’, and ‘Minesweeper’
  Not the PM, ’Santa Claus’, or the ‘Tech Guy’
Project Manager
  The ‘Linchpin’
  Must be ‘multi-lingual’

## Slide 110: Understanding Organizations
Structural frame: Focuses on roles and responsibilities, coordination and control. Organization charts help define this frame.
Human resources frame: Focuses on providing harmony between needs of the organization and needs of people.
Political frame: Assumes organizations are coalitions composed of varied individuals and interest groups. Conflict and power are key issues.
Symbolic frame: Focuses on symbols and meanings related to events. Culture is important.

## Slide 111: Organizational Structures
Functional
  Engineering, Marketing, Design, etc.
  P&L from production
Projectized
  Project A, Project B
  Income from projects
  PM has P&L responsibility
Matrix
  Functional and Project based
  Program Mgmt. Model
  Shorter cycles, need for rapid development process

## Slide 112: Functional Organization
Pros
  Clear definition of authority
  Eliminates duplication
  Encourages specialization
  Clear career paths
Cons
  “Walls”: can lack customer orientation
  “Silos” create longer decisions cycles
  Conflicts across functional areas
  Project leaders have little power

## Slide 113: Projectized Organization
Pros
  Unity of command
  Effective intra-project communication
Cons
  Duplication of facilities
  Career path
Examples: defense avionics, construction

## Slide 114: Matrix Organization
Pros
  Project integration across functional lines
  Efficient use of resources
  Retains functional teams
Cons
  Two bosses for personnel
  Complexity
  Resource & priority conflicts

## Slide 115: Matrix Forms
Weak, Strong, Balanced
Degree of relative power
  Weak: functional-centric
  Strong: project-centric

## Slide 116: Organizational Structure – Influences on Projects
PMBOK Guide, 2000, p. 19

## Slide 117: Common-Sense Approach to Projects
Start on the right foot. This is accomplished by working hard (very hard) to understand the problem that is to be solved and then setting realistic objectives and expectations.
Maintain momentum. The project manager must provide incentives to keep turnover of personnel to an absolute minimum, the team should emphasize quality in every task it performs, and senior management should do everything possible to stay out of the team’s way.
Track progress. For a software project, progress is tracked as work products (e.g., models, source code, sets of test cases) are produced and approved (using formal technical reviews) as part of a quality assurance activity.
Make smart decisions. In essence, the decisions of the project manager and the software team should be to “keep it simple.”
Conduct a postmortem analysis. Establish a consistent mechanism for extracting lessons learned for each project.

## Slide 118: Project Planning

## Slide 119: Project Planning
“Now the general who wins a battle makes many calculations in his temple ere the battle is fought. The general who loses a battle makes but few calculations beforehand. Thus do many calculations lead to victory, and few calculations to defeat”
Sun Tzu, The Art of War

## Slide 120: Software Project Planning
The overall goal of project planning is to establish a pragmatic strategy for controlling, tracking, and monitoring a complex technical project.
Or,
A Plan is the strategy for the successful completion of the project. It's a description of the project steps that produce increasing maturity of the products or processes produced by the project.
Why?
  So the end result gets done on time, with quality!

## Slide 121: Planning
“You've got to be very careful if you don't know where you're going, because you might not get there.”
“If you don't know where you are going, you will wind up somewhere else.”
“If you don't know where you're going, any road will take you there.”
“If you don’t know where you’re going, how do you know when you get there?”
– Yogi Berra
“The nicest thing about not planning is that failure comes as a complete surprise and is not preceded by a period of worry and depression.”
– John Preston, Boston College

## Slide 122: Why plan?
Why plan?
  Consider driving a car: do you drive looking backwards?
Recall from the Standish Group's 2009 CHAOS Report:
  ‘Proper Planning’ was the 4th ranked factor cited for successful projects (just behind ‘Clear Statement of Requirements’)
  ‘Lack of Planning’ was the 7th ranked factor cited for failed projects (just behind ‘Changing Requirements’)
We will soon see that the close correlation of requirements and planning is no coincidence: establishing requirements is an essential part of planning

## Slide 123: Reasons people don’t plan
Don’t believe in planning
  Management or organization culture does not support planning
Find the process painful
  If you do plan, the pain will be greatest early and will diminish with time
  If you don’t plan, you defer the pain (and it will usually be greater…)
Don’t have time to plan!
  Consider the simple task of getting yourself to class
  Now consider having the responsibility of getting all the other people to class on time, not just SE 477 but other classes, as well …

## Slide 124: Planning is essential to control
An effective way to exert control is to:
  Know where you are
  Know where you are supposed to be
  Take corrective action if there is a difference between the two
Note:
  You have to have a plan to know where you are supposed to be
  If you have no plan, you have no control
    Example: Commercial airliner ﬂying from Chicago to Tokyo
Planning and control
  Two phases both needed

## Slide 125: Planning processes
Planning processes determine the total project scope, deﬁne or reﬁne the project objectives, and develop the course of action to achieve the objectives
Planning employs progressive elaboration: the process of revisiting planning (and possibly initiating) processes as additional project information becomes available
The planning processes covered in SE 477 encompass project integration management, project scope management, project time management, project risk management, and project stakeholder management
Notes: Adapted from Figure 2-10 PMBOK Guide, 5th Edition

## Slide 126: Planning
Preliminary planning starts on day one
Even in the pre-project phase
Should not be conducted “in secret”
Need buy-in and approval
  Very important step
  Both from above and below

## Slide 127: Planning
Scoping
  What is the problem
How much will it cost?
  Estimation
How long will it take?
  Schedule
Resources
  How many people will it take?
Risk
  What might go wrong?
Control Strategy

## Slide 128: Planning processes and knowledge areas

## Slide 129: Primary Planning Steps
Identify project scope and objectives
Define and Record Requirements
Identify project organizational environment
  Analyze project characteristics
  Identify Project Team and Define Roles and Responsibilities
Identify project products and activities
  Create the WBS
  Estimate effort for each activity
  Allocate resources
  Schedule deliveries and milestones

## Slide 130: Primary Planning Steps
Develop Change Management Plan
Identify Risks and Define Risk Strategies
Review and communicate plan
Obtain Plan Approval
Conduct Kick-off Meeting

## Slide 131: Project Planning Task Set – I
Establish project scope
Determine feasibility
Define required resources
  Determine required human resources
  Define reusable software resources
  Identify environmental resources
Estimate cost and effort
  Decompose the problem
  Develop two or more estimates using size, function points, process tasks or use-cases
  Reconcile the estimates

## Slide 132: Project Planning Task Set – II
Develop a project schedule
  Scheduling is considered in detail later.
    Establish a meaningful task set
    Define a task network
    Use scheduling tools to develop a timeline chart
    Define schedule tracking mechanisms
Analyze risks
  Risk analysis is considered in detail later.

## Slide 133: Software Project Survival Guide
Documents
  Plans, reports
Schedules
Checklists

## Slide 134: Process Issues
You want a fairly sophisticated process without incurring much overhead
Remember, projects are often larger than they first appear
Easier to loosen too much process than add later

## Slide 135: Plans Evolve Over Time
NASA's “Manager's Handbook for Software Development”

## Slide 136: Software Development Plan (SDP)
Software Project Management Plan (SPMP)
Some consider it the most important document in the project (along with requirements document)
  Can be seen as an aggregation of other core documents
Evolves over time as pieces come together

## Slide 137: SDP / SPMP
Fundamental Sections
Project overview
Deliverables
Project organization
Managerial processes
  Communication management plan
  Milestones
Technical processes
Budget
Schedule

## Slide 138: Preliminary Scope
Project objectives
Product description
Product objectives
Product deliverables
Requirements (product and project)
Exclusions (project boundary)
Constraints
Assumptions
High-level risks and definitions
Milestones
Initial WBS
Cost Estimate
Configuration management requirements
Project acceptance criteria
Notes: PMP Guide – p. 75

## Slide 139: Deliverables
List of items to be delivered
  Must be tangible items
Sample deliverables
  The product – the actual software, in the installable format
  Product documentation
  Reports and planning documentation
Most projects are driven by deliverables, so you need several
Project deliverables (aka documents) are included

## Slide 140: Communications Management Plan
Often a section of Software Project Management Plan (SPMP)
Describes information flow to all parties
  Gathering and distributing information
Status meetings
  Monthly, Weekly, Daily?
  Status reports are vital
Stakeholder Management Plan

## Slide 141: Documents
Two kinds of documents
Planning
Product
Let us review each kind …

## Slide 142: Planning Documents
Project ROI Analysis
  Business Case (include competitive analysis if appropriate)
Project Charter
  Statement of Work (SOW)
Software Project Management Plan (SPMP)
  Software Development Plan (SDP)
    Schedule
  Communications Management Plan
Budget
Responsibility Assignment Matrix (RAM)
Risk Management Plan

## Slide 143: Planning Documents
Other documents you may want/need
Software Quality Assurance Plan (SQAP)
  Software Process Improvement Plan
Software Configuration Management Plan (SCMP)
Migration Plan
Operations Plan

## Slide 144: Planning Documents
You (the PM) need to choose which documents are appropriate
Docs do not have to be lengthy
Small Set:
  Software Development Plan
  Risk Management Plan
  Software Quality Assurance Plan
  Software Configuration Management Plan

## Slide 145: Product Documents
Statement of Need
System Interface Specification
Software Requirements Specification
Software Design Specification
Software Validation & Verification Plan
User Documentation
Support Plan
Maintenance Documentation

## Slide 146: Project Phases

## Slide 147: Potential Deliverables by Phase

## Slide 148: Time Allocation by Phase
Remember the 40-20-40 Rule
  Specification-Implementation-Test
 | Planning | Code & Unit Test | Integration & Test
Commercial DP | 25% | 40% | 35%
Internet Systems | 55% | 15% | 30%
Real-time Systems | 35% | 25% | 40%
Defense Systems | 40% | 20% | 40%
Bennatan, E.M, “On Time Within Budget”
Notes: The 40-20-40 rule emphasizes strong front-end design (40%) and back-end testing (40%), whereas the mechanical programming (coding) task is de-emphasized (20%).

## Slide 149: Time Allocation by Phase
Activity | Small Project (2.5K LOC) | Large Project (500K LOC)
Analysis | 10% | 30%
Design | 20% | 20%
Code | 25% | 10%
Unit Test | 20% | 5%
Integration | 15% | 20%
System test | 10% | 15%
McConnell, Steve, “Rapid Development”

## Slide 150: Activities by % of Total Effort
NASA's “Manager's Handbook for Software Development”

## Slide 151: Conventional planning approach
Planning seems to be a straightforward process:
  Determine the tasks to be done
  Determine the order of the tasks
  Execute the tasks in the proper order
Uncertainty can, and usually does, disrupt this ﬂow
  Not every task can be identiﬁed before the project starts
  Contingent factors—internal or external—add, delete, or modify tasks
  Task ordering is changed due to new or unforeseen dependencies
At their very foundations, conventional planning approaches implicitly assume an unrealistic model of human cognition and behavior, while ignoring or underestimating real-world risk

## Slide 152: Planning in an IID methodology
In contrast to big, up-front planning or even planning in conventional iterative and incremental methodologies, an IID methodology spreads planning out over the entire project lifecycle
Planning in an IID methodology:
  Distributes planning from the top-level stakeholders to the individual developers—each plans at the appropriate scale
  Delays ﬁne-grained planning to ‘just-in-time’ before corresponding task or activity
  Is low-overhead—‘barely sufﬁcient’ planning documents are lightweight and the majority are produced ‘as-needed’ rather than as a matter of protocol
  Is resilient to requirements changes—it embraces change rather than attempts to prevent or avoid it

## Slide 153: Planning In The Iterative Development Model
Needs to take into consideration the iterations
See slides 45-51, 92-96 of lecture 2
See PMBOK-SWE Ch. 2.4.2.3
See also: Kruchten, P (2002, Oct 15) Planning an Iterative Project: http://www.ibm.com/developerworks/rational/library/2831.html