## Slide 1: Introduction
SE423: Software Project Management

## Slide 2: Outline
Introduction
Projects
What is Project Management?
Software Project Management
Factors in Project Success & Failure
Project Dimensions
Projects vs Programs
Suggested Skills for PM
Project Management History

## Slide 3: Introduction

## Slide 4: Software Engineering
What do the following have in common?
  Civil Engineering
  Mechanical Engineering
  Industrial Engineering
  Chemical Engineering
  Electrical Engineering
  Software Engineering
They all have common themes:
  Product Design
  Process Creation and Refinement
  Project Activity

## Slide 5
Quality Factors:
  Usability
  Reliability
  Safety
  Well constructed
  Use of technology
  Aesthetically pleasing
Also consider:
  Costs (within budget)
  Schedule (on time)
  Maintainability
What does “Well Engineered” Mean?

## Slide 6: Introduction
Many people and organizations today have a new or renewed interest in project management
The Project Management Institute reported that by 2027, employers will need 87.7 million individuals working in project management–oriented roles.
According to PMI’s 2021 Talent Gap report, 2.3 million new project management employees will be needed each year to meet global talent demands by 2030.

## Slide 7: Introduction
The top skills employers look for in new college graduates are all related to project management: team-work, problem-solving, and verbal communications.
Organizations waste $97 million for every $1 billion spent on projects, according to PMI’s Pulse of the Profession® report.
The Saudi Smart Government Strategy is expected to set Saudi Arabia’s AI market to touch $135.2 billion by 2030, which is estimated to contribute 12.4 percent to the Kingdom’s gross domestic product.
Saudi Arabia’s government spending on technology has been valued at around $24.7 billion (SR 93 billion) by 2025, the highest in the world, accounting for 21.7 percent of national spending

## Slide 8: Introduction
Advantages of Using Formal Project Management:
  Better control of financial, physical, and human resources
  Improved customer relations
  Shorter development times
  Lower costs and improved productivity
  Higher quality and increased reliability
  Higher profit margins
  Better internal coordination
  Positive impact on meeting strategic goals
  Higher worker morale (less stress)
    Less “death marches”
    Less overworked personnel

## Slide 9: What Went Wrong?
IT Projects have a terrible track record, as described in the What Went Wrong?
A Standish Group study (CHAOS) in 2017 found that only 28% of IT projects were successful in meeting scope, time, and cost goals; over 18% of IT projects were canceled before completion
A PricewaterhouseCoopers study found that over half of all projects fail and only 2.5% of corporations consistently meet their targets for scope, time, and cost goals for all types of project

## Slide 10: Projects

## Slide 11: What is a project?
What’s a project?
PMI definition
  A project is a temporary endeavor undertaken to create a unique product or service
Better: A sequence of connected and related activities (requirement engineering, system engineering, coding, testing, documentation, controlling, …) that must be completed by a specific time, within budget, and according to specification.
Progressively elaborated
  With repetitive elements
A project manager
  Analogy: conductor, coach, captain
Notes: Temporary:
  can be years
  Result can be lasting
  Team can be temporary
Finite duration
Ex: thousands of buildings, but each is unique
Scope should be constant even as elaboration happens

## Slide 12: What Is a Project?
A project is “a temporary endeavor undertaken to create a unique product, service, or result” (PMBOK® Guide, Sixth Edition, 2017)
Operations is work done to sustain the business
Projects end when their objectives have been reached or the project has been terminated

## Slide 13: Examples of IT Projects
A team of students creates a smartphone application and sells it online
A company develops a driverless car
A government group develops a system to track child immunizations
A global bank acquires other financial institutions and needs to consolidate systems and procedures

## Slide 14: Examples of IT Projects
Top Strategic Technologies for 2023 (Gartner)
  Sustainability
  Metaverse
  Superapps
  Adaptive AI
  Digital Immune System
  Applied Observability
  AI Trust, Risk and Security Management
  Industry Cloud Platforms
  Platform Engineering
  Wireless Value Realization

## Slide 15: Media Snapshot
Gartner Predicts 80% of Customer Service Organizations Will Abandon Native Mobile Apps in Favor of Messaging by 2025
TikTok is by far the most downloaded app, and the most popular category of all apps continues to be games
Mobile apps are expected to generate over $935 billion in revenue by 2023.
There are 2.87 million apps available for download on the Google Play Store.
21% of Millennials open an app 50+ times per day.
49% of people open an app 11+ times each day.

## Slide 16: Project vs. Program Management
What’s a ‘program’?
Mostly differences of scale
Often a number of related projects
Longer than projects
Definitions vary
Example: Program Manager for MS Office
  Includes projects: Spelling, drawing, Word, Xcel, PowerPoint, etc.

## Slide 17: Project characteristics
A project is unique
  A Project creates unique deliverables: product, service, or result
  Even technically-identical projects are distinctly unique, due to internal or external contingent factors
Projects are temporary
  Every project has a deﬁnite beginning and a deﬁnite end
  Project end may be reached through success, qualiﬁed success, failure, or redundancy
  Projects need not be of short duration, but they are of ﬁnite duration

## Slide 18: Project characteristics
Projects have customer-speciﬁed performance criteria
  The customer deﬁnes these criteria in the form of requirements
  We will see that requirements are one of the most critical characteristics of a project that contributes to its success or failure
Projects consume resources
  Personnel resources
  Physical resources
  Monetary resources

## Slide 19: Project vs Operational
Projects
  Have a Beginning and End
  Have Unique Goals/Objectives
  Are not ‘Business as Usual’
Operational Work
  Most ongoing work
  Often completed projects are handed off to ‘operations’
  ‘Business as Usual’
Each has very different management techniques, although some core skills and competencies are the same

## Slide 20: Projects vs. operations/production

## Slide 21: Characteristics of IT (Information Technology)
IT encompasses all forms of technology used to create, store, exchange, and use information in various forms
‘Information’ includes conventional data, voice, images, multimedia, etc.
Of central importance are computer, software, and communications technologies
Virtually all signiﬁcant projects are now distributed: networks of computers communicate only via message passing
Distribution poses additional challenges in IT projects: reliability, availability, security, and information synchronization

## Slide 22: How do IT projects differ from ‘ordinary’ projects?
IT products and services possess greater complexity
  IT products and services are intrinsically complex by nature
  Computing + communication + diverse data ⇒ complexity
IT projects have tight schedules
  Tight schedules are the norm in IT development
  Scheduling is aggravated by a pervasive ‘rush to market’ mentality
IT is an integral part of enterprise infrastructure
  IT is no longer an auxiliary element of the enterprise
  A business’ success is often critically dependent upon IT support
IT is permeated by quickly-changing technology
  Technology evolves (and may even become obsolete) during the lifetime of a major project

## Slide 23: Project characteristics
Four characteristics of projects:
  finite time
  people assigned
  clear roles and responsibilities
  things to deliver
Have you ever had this feeling about a project?
  not enough time
  too few people
  people not sure what they should be doing
  too much to do

## Slide 24: How Are Software Projects Different?
Consists of hardware and software.
Software is [usually] custom written and one-of-a-kind.
Hard to determine progress. [One can see how far the Freedom Tower (World Trade Center) has progressed. One cannot see how far a piece of software has progressed]
Difficult to estimate schedule.
Difficult to determine cost.

## Slide 25: Project Attributes
A project
  has a unique purpose
  is temporary
  drives change and enable value creation
  is developed using progressive elaboration
  requires resources, often from various areas
  should have a primary customer or sponsor
    The project sponsor usually provides the direction and funding for the project
  involves uncertainty
Project managers work with project sponsors, team, and other people involved in a project to achieve project goals

## Slide 26: Project Constraints

## Slide 27: Process and Project Management
“A process is a series of steps involving activities, constraints and resources that produce an intended output of some kind.”
Processes need to be appropriate both for the type of development organization and the type of application being developed.

## Slide 28: Product Lifecycle

## Slide 29: Project Lifecycle

## Slide 30: Project Lifecycle

## Slide 31: What is Project Management?

## Slide 32: Thought for the day
"The first 90% of a project takes 90% of the time, the last 10% takes the other 90%."

## Slide 33: What is Project Management?
Project management is “the application of knowledge, skills, tools and techniques to project activities to meet project requirements”.
Project managers strive to meet the triple constraint (project scope, time, and cost goals) and also facilitate the entire process to meet the needs and expectations of project stakeholders.

## Slide 34: Project Terms
Project Sponsor
Stakeholders
Scope
Project Charter
Project Management Office (PMO)
Postmortem

## Slide 35: Project Stakeholders
Stakeholders are the people involved in or affected by project activities
Stakeholders include
  the project sponsor
  banks and other financial institutions
  the project manager
  the project team
  support staff
  suppliers
  opponents to the project

## Slide 36: Project Management Knowledge Areas
Knowledge areas describe the key competencies that project managers must develop
Project managers must have knowledge and skills in all 10 knowledge areas (scope, schedule, cost, quality, resource, communications, risk, procurement, stakeholder, and project integration management)
This text includes an entire chapter on each knowledge area

## Slide 37: Project Management Tools and Techniques
Project management tools and techniques assist project managers and their teams in various aspects of project management
Some specific ones include
  Project charter, scope statement, and WBS (scope)
  Gantt charts, network diagrams, critical path analysis, critical chain scheduling (time)
  Cost estimates and earned value management (cost)
  See Table 1-1 for many more

## Slide 38: Project Management Tools and Techniques
PMBOK® Guide – Sixth Edition lists tools and techniques based on their purpose:
  Data gathering
  Data analysis
  Data representation
  Decision making
  Communication
  Interpersonal and team skills
  Ungrouped

## Slide 39: Software Project Management

## Slide 40: What is Project Management?
A Discipline
Planning, Organizing, Motivating, and Controlling resources to achieve defined goals.
Requires the Development of Distinct Technical and Management Skills
Projects
  Have a Beginning and End
  Have Unique Goals/Objectives
  Are Not Business as Usual

## Slide 41: Managing Engineering Process
Traditional Engineering
  Developing Schedules
  Establishing Budgets
  Securing & Allocating Resources
  Managing Risks
  Tracking Progress
  Coordinating Teams (often across organizational boundaries)
Software Engineering
  Formulate the problem
  Design, Modeling, Prototyping
  Evaluate different solutions / trade-offs
  Detailed Technical Specifications
  Construction or Manufacturing
  Testing / Evaluation
  Delivery & Maintenance

## Slide 42: What is Project Management?
Project management is “the application of knowledge, skills, tools and techniques to project activities to meet project requirements”
Software Project Management is the art to define, plan, execute, and monitor the activities that will bring software products to existence.
Project managers strive to meet the triple constraint by balancing project scope, time, and cost goals

## Slide 43: Project management processes
Regardless of the type of project lifecycle, project management encompasses the following process groups, shown with some representative tasks:
  Initiating/Define – Scope the project; Charter the project; identify stakeholders
  Planning – Develop the project plan. Collect requirements; identify schedule; plan scope, cost, quality, human resource, risk, and procurement management
  Executing – Launch the plan. Direct and manage project work; perform quality assurance; manage and develop project team; conduct procurements
  Monitoring and Controlling – Monitor project progress. Monitor and control project work; manage scope change; monitor and control schedule; control quality; control risks; control procurements
  Closing – Close out the project: Close project; close procurements
Notes: For some lifecycle types, some of the tasks are irrelevant or appear a radically different form; e.g., scope management in an adaptive (agile) lifecycle vs. predictive (conventional linear) lifecycle

## Slide 44: Software Project
Quality Engineering Principle:
The quality of the software system is controlled by the quality of the process used to produce that software.
Quality Management Principle:
Document the process
Measure the process
Improve the process based on the measurement

## Slide 45: Software Development Process
What is the software development process?
  A process is a set of documented procedures, methods, practices, and tools used to produce a software product.
The process will answer the following:
  What to do? Tasks/activities
  How to do it? Procedure/practice
  When to do it? Sequence of activities
  What are the artifacts? (input/output)

## Slide 46: Software Project
If the programmer and designer follow the process, then the artifacts they produce will be
  Predictable
  Based on the requirements
  Easy to maintain and control
  Consistent with the writing style
  Of acceptable quality
  Within acceptable milestones
By following the process, we will be able to know precisely what/how/when/where it happened !

## Slide 47: Software Processes
Software Process is an overloaded term
Metaprocess: an organization’s policies, procedures, and practices for pursuing a software-intensive line of business; the focus is on organizational economics, and long-term strategies.
Macroprocess: the project’s policies, procedures, and practices for producing a complete software product within certain cost, schedule, and quality constraints.
Microprocess: a project team’s policies, procedures, and practices for achieving an artifact of the software process.

## Slide 48: Core project management activities
Identify requirements
Address the various needs, concerns, and expectations of the stakeholders in the project
Establish active, effective, collaborative communications among the stakeholders
Manage stakeholders towards meeting project requirements and creating project deliverables
Balance the competing project constraints, including: scope, quality, schedule, budget, resources, and risks

## Slide 49: Software Project Trade-offs
What is the goal?
Balance the main three (other 2 constraints scope and resource) … in order to:
  Stay within the budget (cost)
  Deliver on time to gain market share (time)
  Exceed customer satisfaction (quality)
The time/scheduling hypocrisy
What can you tell me about the next project, you ask?
  It is due on June 1st tells your manager
We hold deadlines too dearly. Of course, time to market is critical
But what generally happens on projects when you hit that deadline?

## Slide 50: What makes a project successful?
Successful project management means meeting all three goals (scope, time, cost) – and satisfying the project’s sponsor.
Trade-off Triangle
Project constraints: Fast, cheap, good. Choose two. Also stated as: “On-time, on-budget, high-quality. Choose two.”
  Reality often ignored in project planning
Know which of these are fixed & variable for every project
  Time
  Cost
  Scope

## Slide 51: The Project Triangle
Good, Fast, Cheap – Pick 2
Quality, Resources, Schedule

## Slide 52: Success Metrics
On schedule
  Requires good: plan; estimation; control
Within budget
  Again: planning, estimation & control
According to requirements
  Importance of good requirements
  Perception & negotiation critical
High quality. May or may not be same as item 3
Only real measure:
  Is the customer happy?
  Customer satisfaction!!

## Slide 53: Factors in Project Success & Failure

## Slide 54: Successful Projects
What makes a project successful?
  Avoiding Mistakes
  Strong Teams
  Managing Risks
  Proper Planning
  Understanding Good Methodology
  Good Estimation (Looking ahead)
  Good Perspective (Looking Back –
  Measurement & Metrics)
  Proper Testing
  Results and a Happy Customer

## Slide 55: Project Success (1 of 4)
There are several ways to define project success:
  The project met scope, time, and cost goals
  The project satisfied the customer/sponsor
  The results of the project met its main objective, such as making or saving a certain amount of money, providing a good return on investment, or simply making the sponsors happy

## Slide 56: Project Success (2 of 4)
Factors of Success | Points
Executive sponsorship | 15
Emotional maturity | 15
User involvement | 15
Optimization | 15
Skilled resources | 10
Agile processes | 7
Modest execution | 6
Project management expertise | 5
Clear business objectives | 4
Source: The Standish Group, CHAOS Manifesto 2015 (2015)
Table: What Helps Projects Succeed?

## Slide 57: Project Success (3 of 4)
Top three reasons why federal technology projects succeed
  Adequate funding
  Staff expertise
  Engagement from all stakeholders

## Slide 58: Project Success (4 of 4)
Research findings show that companies that excel in project delivery capability:
  Use an integrated toolbox
  Grow project leaders
  Develop a streamlined project delivery process
  Measure project health using metrics, like customer satisfaction or return on investment

## Slide 59: How Do Projects Succeed?
Executive support
Experienced project manager
Clear business objectives and priorities
Minimized scope
Standardized infrastructure
Firm basic requirements
Predictable costs
Communication between parties
Formal methodology
Reliable estimates

## Slide 60: Software Crisis
Many software-related failures: auto-pilot systems, air traffic control systems, banking systems, IRS.
  On January 15, 1990, the AT&T long-distance telephone network broke down, interrupting long-distance telephone services in US for over 8 hours. [Missing break in a switch statement.]
  On June 4, 1996, the maiden flight of the new and improved Ariane 5 rocket exploded 37 seconds after lift-off.
  On June 8, 2001, a software problem caused the NYSE to shut down the entire trading floor for over an hour.
  Many, many, many more.

## Slide 61: Why do IT projects fail?
Requirements, requirements, requirements
  Requirements are unclear, incomplete, or the project management methodology does not accommodate changing requirements effectively
Lack of user involvement
  A disengaged or absentee user (~customer) is an invitation for project problems or outright failure
  Often the result of a lack of business and IT integration
Unrealistic expectations (including unrealistic time frame expectations)
  Closely related to/result of ‘Lack of user involvement’
  “How hard can it be?” attitude of business and technical management
  Overly optimistic ‘can do’ attitude at all levels
  It is the project management team's responsibility to educate users in the realities of the project

## Slide 62: Why do IT projects fail?
Lack of planning
  You cannot achieve any goal without planning
  Proper approach to planning in a complex project must be adaptive: big planning up front is a waste of time and gives a false sense of security
  Related issues: Perceived rush to get started; overconﬁdence
Unclear (or lack of) vision and/or objectives
  The project vision must be established as one of the ﬁrst steps in project planning
  The vision for a project should be short, concise, and laser-sharp: the ‘elevator statement’ format is most effective

## Slide 63: Why do IT projects fail?
36 Classic Mistakes
AntiPatterns [see lecture 9]
Seductive Appeal: good reason for decisions at the time
Types
  People-Related
  Process-Related
  Product-Related
  Technology-Related
Gilligan’s Island
Notes: Seductive: good reason for decisions at the time
We’ll visit these throughout course
Gilligan’s Island: new scheme, get off island, seems to work, then fails
Being aware can help prevent
Class discussion

## Slide 64: People-Related Mistakes Part 1
Undermined motivation
Weak personnel
  Weak vs. Junior
Uncontrolled problem employees
Heroics
Adding people to a late project
Lack of match between people and needs
  Incompetent or over competent
  Culture clash
Notes: Motivation: studies show has largest impact
  Don’t undermine Morale
2nd greatest influence on productivity
  Junior != bad
Uncontrolled: most common developer complaint about their managers
Heroics. Company hostage.
  “Can-do”, “how high” attitudes
Brooks, reading assignment

## Slide 65: People-Related Mistakes Part 2
Noisy, crowded offices
Customer-Developer friction
  Unrealistic expectations
  Lack of user input
Politics over substance
Lack of effective project sponsorship
Lack of stakeholder buy-in
Wishful thinking
Notes: 60%of developers feel unsatisfactory environment: need quite and privacy
  real offices
Friction: classic differing viewpoints
  Results in ‘poor communication’
    Passive-aggressive
  User input: Survey: number 1 reason for success
    W/O input: guessing
  Realistic Expectations: 1 of top 5 reasons for success of in-house projects
    Perception woe
Politics
  Managing-up
Sponsor: a must, no power
All players must buy-in
Wishful
  Cognitive dissonance
  Closing your eyes and hoping
  McConnell: maybe causes the most problems in software development

## Slide 66: Process-Related Mistakes Part 1
Optimistic schedules
  Omitting necessary tasks from estimates
  Planning to catch-up later
  Code-like-hell programming
  Insufficient risk management
Contractor failure
Insufficient planning
Abandonment of plan under pressure
Notes: Similar to wishful thinking
  Puts unnecessary pressure
  Missing tasks
    Often 20-30% of a schedule
  Catch-up later
    How many times have you seen a project catch-up?
    Only by all-nighters
  Like hell
    “Entrepreneurial” approach
Management controls
  Need to be able to track
  We’ll cover lots of these
  PMI
  See catch-up later
Risk Mgmt:
  Risks will manage you
Contractor: late, poor quality, or fails to meet specifications
  Requires lots of management
Insufficient planning: “if you don’t care where you’re going, any plan will do”
Abandonment
  Out the window
  Fall into code-and-fix mode

## Slide 67: Process-Related Mistakes Part 2
Wasted time during fuzzy front end
Shortchanged upstream activities
Inadequate design
Shortchanged quality assurance
Insufficient management controls
Frequent convergence
Notes: fuzzy: before sign-off
Upstream:
  Lack of analysis and design
  10 to 100 times more costly
  5 hrs vs. 50
Design:
  Seen schedules w/o it at all
QA:
  Seems easy to compress
  1 day QA == 3 to 10 later
Convergence
  Waste of time

## Slide 68: Product-Related Mistakes
Requirements gold-plating
  Gilding the lily
Feature creep
Developer gold-plating
  Beware the pet project
Push-me, pull-me negotiation
  Slip schedule + add features
Research-oriented development
Notes: Gold
  Gilding the lily
  Performance is required more often than need be
Feature creep
  25% average change in req.
Dev. Gold
  Nifty new technology
  Pet project
Push-me
  Slip schedule + add features
Research vs. Development

## Slide 69: Technology-Related Mistakes
Silver-bullet syndrome
Overestimated savings from new tools and methods
  Fad warning
Switching tools in mid-project
Lack of automated source-code control
Notes: who’s heard of ‘silver bullet’ (not the beer)
Software savings on SCM
  Jones: 10% month, I see more

## Slide 70: What Helps Projects Succeed?
Executive support
User involvement
Experienced project manager
Clear business objectives
Minimized scope
Standard software infrastructure
Firm basic requirements
Formal methodology
Reliable estimates
Other criteria, such as small milestones, proper planning, competent staff, and ownership

## Slide 71: Project Dimensions

## Slide 72: Project Dimensions

## Slide 73: Four Project Dimensions
Four Project Dimensions (The 4 P's)
People — the most important element of a successful project
Product — the software to be built
Process — the set of framework activities and software engineering tasks to get the job done
Project — all work required to make the product a reality
Notes: Peopleware issues
  10-to-1 difference in Dev productivity
  Teams 3 or 5 to 1 diff
Process
  Dev basics, risk mgmt, QA, lifecycle planning, customer orientation
Product
  Most tangible dimension

## Slide 74: People
“It’s always a people problem”
– Gerald Weinberg, “The Secrets of Consulting”
Developer productivity: 10-to-1 range
  Teams 3 (or 5) to 1 difference
Improvements:
  Team selection
  Team organization
  Motivation
Other success factors
  Matching people to tasks
  Career development
  Balance: individual and team
  Clear communication
Notes: Teams: 5-to-1 range

## Slide 75: Product
The “tangible” dimension
Product size management
Product characteristics and requirements
Feature creep management

## Slide 76: Process
Is process stifling?
  2 Types: Management & Technical
Development fundamentals
Quality assurance
Risk management
Lifecycle planning
Avoid abuse by neglect
Customer orientation
Process maturity improvement
Rework avoidance
Goals
  cut time-to-market
  Improve quality
Notes: cut time-to-market
Improve quality

## Slide 77: Technology
Often the least important dimension
Language and tool selection
Value and cost of reuse

## Slide 78: Planning
Determine requirements
Determine resources
Select lifecycle model
Determine product features strategy
Tracking
  Cost, effort, schedule
  Planned vs. Actual
  How to handle when things go off plan?

## Slide 79: Measurements
To date and projected
  Cost
  Schedule
  Effort
  Product features
Alternatives
  Earned value analysis
  Defect rates
  Productivity (ex: SLOC)
  Complexity (ex: function points)

## Slide 80: Technical Fundamentals
Assumed Software Development Life Cycle (SDLC)
Requirements
Analysis
Design
Construction
Quality Assurance (aka Testing)
Deployment

## Slide 81: Projects vs Programs

## Slide 82: Program and Project Portfolio Management
About one-quarter of the world’s gross domestic product is spent on projects
Two important concepts that help projects meet enterprise goals:
  Use of programs
  Project portfolio management

## Slide 83: Programs
A program is “a group of related projects managed in a coordinated manner to obtain benefits and control not available from managing them individually” (PMBOK® Guide — Sixth Edition, 2017)
Examples of common programs in the IT field include infrastructure, applications development, and user support
A program manager provides leadership and direction for the project managers heading the projects within the program

## Slide 84: Project Portfolio Management
As part of project portfolio management, organizations group and manage projects and programs as a portfolio of investments that contribute to the entire enterprise’s success
Portfolio managers help their organizations make wise investment decisions by helping to select and analyze projects from a strategic perspective

## Slide 85: Project Portfolio Management

## Slide 86: Best Practice
A best practice is “an optimal way recognized by industry to achieve a stated goal or objective”*
Robert Butrick suggests that organizations need to follow basic principles of project management, including these two mentioned earlier in this chapter:
  Make sure your projects are driven by your strategy. Be able to demonstrate how each project you undertake fits your business strategy, and screen out unwanted projects as soon as possible
  Engage your stakeholders. Ignoring stakeholders often leads to project failure. Be sure to engage stakeholders at all stages of a project, and encourage teamwork and commitment at all times

## Slide 87: Organizational Structure
Functional
  Most Common “Classic”
  Grouped by specialization
  Team members have both departmental and project work
Projectized
  Project is king
  Staff are moved from project to project
Matrix
  The two types mixed
  Two bosses, Project Boss and Functional Boss

## Slide 88: Organizational Project Management
Organizational project management
  Framework in which portfolio, program, and project management are integrated with organizational enablers in order to achieve strategic objectives

## Slide 89: Suggested Skills for PM

## Slide 90: The Role of the Project Manager
Project managers must work closely with the other stakeholders on a project, especially the sponsor and project team
They are also more effective if they are familiar with the 10 project management knowledge areas
  And the various tools and techniques related to project management

## Slide 91: Project Manager Job Description
Job descriptions vary, but most include responsibilities like planning, scheduling, coordinating, and working with people to achieve project goals
Project management is a skill needed in every major IT field, from database administrator to network specialist to technical writer

## Slide 92: Advice for Young Professionals
A few questions to ask yourself to know if you would be a good project manager
  Do you get frustrated by bad bosses? Do you think you could do a better job?
  Are you interested in understanding the big picture of how organizations work and how your individual work or your project fits in?
  Have you had other leadership roles, such as being a team captain, president of a club, or entrepreneur of a small business? Did you enjoy it? Did others think you did a good job?
  Are you good at mentoring others? Do people ask you for help in developing their skills or your advice on what to do?

## Slide 93: Suggested Skills for Project Managers
The Project Management Body of Knowledge
Application area knowledge, standards, and regulations
Project environment knowledge
General management knowledge and skills
Soft skills or human relations skills

## Slide 94: Suggested Skills for Project Managers
Six traits of highly effective project managers as follows:
  Be a strategic business partner
  Encourage and recognize valuable contributions
  Respect and motivate stakeholders
  Be fully vested in success
  Stress integrity and accountability
  Work in the gray/Be able to deal with ambiguity

## Slide 95: PMI Talent Triangle® and the Importance of Leadership Skills*
The talent triangle includes:
  Technical project management skills
  Strategic and business management skills
  Leadership skills
Leadership styles include:
  Laissez-faire
  Transactional
  Servant leader
  Transformational
  Charismatic
  Interactional

## Slide 96: Careers for IT Project Managers
In a 2021 survey, IT executives listed the “ten hot tech skills” they planned to hire for in 2022
Project management was second only to Data Science
Even if you choose to stay in a technical role, you still need project management knowledge and skills to help your team and organization

## Slide 97: Careers for IT Project Managers
1. | Data Science
2. | Project management
3. | Cyber-security
4. | Cloud Computing
5. | User experience/user interface (UX/UI) design
6. | Quality assurance (QA)/testing
7. | Artificial Intelligence
8. | DevOps
9. | Blockchain
10. | Augmented Reality (AR) and Virtual Reality (VR)
Table: Ten hot tech skills for 2012

## Slide 98: Project Management History

## Slide 99: The Project Management Profession
The profession of project management is growing at a very rapid pace
It is helpful to understand the history of the field, the role of professional societies like the Project Management Institute, and the growth in project management software

## Slide 100: History of Project Management
Some people argue that building the Egyptian pyramids was a project, as was building the Great Wall of China.
Most people consider the Manhattan Project to be the first project to use “modern” project management.
This three-year, $2 billion (in 1946 dollars) project had a separate project manager and a technical manager.

## Slide 101: History of Project Management

## Slide 102: History of Project Management
In the 1990s, many companies began creating PMOs to help them handle the increasing number and complexity of projects
A Project Management Office (PMO) is an organizational group responsible for coordinating the project management function throughout an organization

## Slide 103: Global Issues
Several global dynamics are forcing organizations to rethink their practices:
  Talent development for project and program managers is a top concern
  Basic project management techniques are core competencies
  Organizations want to use more agile approaches to project management
  Benefits realization of projects is a key metric

## Slide 104: The Project Management Institute
The Project Management Institute (PMI) is an international professional society for project managers founded in 1969
PMI has continued to attract and retain members, reporting more than 652,000 members worldwide by late 2020
There are communities of practices in many areas, like information systems, financial services, and health care
Project management research and certification programs continue to grow

## Slide 105: Project Management Certification
PMI provides certification as a Project Management Professional (PMP®)
A PMP® has documented sufficient project experience, agreed to follow a code of ethics, and passed the PMP® exam
The number of people earning PMP® certification is increasing quickly
Students can join PMI at a reduced fee and earn the Certified Associate in Project Management (CAPM) certification(see PMI for details)

## Slide 106: Project Management Certification

## Slide 107: Ethics in Project Management
Ethics, loosely defined, is a set of principles that guide our decision making based on personal values of what is “right” and “wrong”
Project managers often face ethical dilemmas
In order to earn PMP® certification, applicants must agree to PMI’s Code of Ethics and Professional Conduct
Several questions on the PMP® exam are related to professional responsibility, including ethics

## Slide 108: Getting organized
So, … now what?
Who is involved?
  Stakeholders
What do they want done?
  Charter, vision, requirements
Who do we have available to do the work?
  Resources and staffing
How do we do this?
  Project planning, WBS
How much will it cost
  Estimating
When will it be finished?
  Scheduling
What can possibly go wrong?
  Risk Management

## Slide 109: Summary
A project is a temporary endeavor undertaken to create a unique product, service, or result
Project management is the application of knowledge, skills, tools, and techniques to project activities to meet project requirements
A program is a group of related projects managed in a coordinated way
Project portfolio management involves organizing and managing projects and programs as a portfolio of investments
Project managers play a key role in helping projects and organizations succeed
The project management profession continues to grow and mature

## Slide 110: Summary of essential points
Projects and operations have both similarities and differences
Complex projects exhibit highly contingent behavior, are unpredictable, and face complex risks
Virtually all IT projects should be considered complex projects
Complex project management requires integration of signiﬁcant sociological, psychological, and technical skills
The factors contributing to project success and failure are reasonably well-known